## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina-I | Burdwan Division | RASUIKHANDA PIPED WATER SUPPLY SCHEME | SM/16253 | New | Continuation order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte for the period of 01.12.2023 to 31.05.2024 | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001007/2023-2024 | 2751/BSD | 28/11/2023 | 29/05/2024 | SK.ASFIA | 2.4 | 0.4 | 16.65 | 70
2 | PURBA BARDHAMAN | Raina-I | Burdwan Division | RASUIKHANDA PIPED WATER SUPPLY SCHEME | SM/16253 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to GOPALPUR & RASUIKHANDA Piped Water Supply Scheme under Raina-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000006/2023-2024 | 1691/BWD | 12/04/2023 | 31/03/2025 | SK ALIM | 1081.52 | 606.84 | 56.11 | 92
3 | PURBA BARDHAMAN | Raina-I | Central Mechanical | RASUIKHANDA PIPED WATER SUPPLY SCHEME | SM/16253 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Rasuikhanda Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000184/2023-2024 | 2968/CMD | 17/07/2023 | 02/07/2024 | ORIENTAL ENGINEERING CO. | 28.96 | 23.34 | 80.61 | 90
4 | PURBA BARDHAMAN | Raina-I | Burdwan Division | RASUIKHANDA PIPED WATER SUPPLY SCHEME | SM/16253 | New | Material Requisition To Resource Division |  |  | RTOR000184/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 7.15 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina-I | Burdwan Division | RASUIKHANDA PIPED WATER SUPPLY SCHEME | SM/16253 | New | Material Requisition To Resource Division |  |  | RTOR000484/2023-2024 | 4008/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 2.23 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina-I | Burdwan Division | RASUIKHANDA PIPED WATER SUPPLY SCHEME | SM/16253 | New | Material Requisition To Resource Division |  |  | RTOR000688/2023-2024 | 5065/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina-I | Central Mechanical | RASUIKHANDA PIPED WATER SUPPLY SCHEME | SM/16253 | New | New service connection charges for Rasuikhanda PWSS TW-2 |  |  | BILL/01426/2023-2024 | BP-2023-24-153 | 05/09/2023 | 05/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.7 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Raina-I | Central Mechanical | RASUIKHANDA PIPED WATER SUPPLY SCHEME | SM/16253 | New | New service connection charges for Rasuikhanda PWSS TW 1 |  |  | BILL/01371/2023-2024 | BP-2023-24-139 | 25/08/2023 | 25/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.04 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Raina-I | Central Mechanical | RASUIKHANDA PIPED WATER SUPPLY SCHEME | SM/16253 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 25/11/2024 | DEY ENTERPRISE | 74.58 | 0 | 0 | 10
10 | PURBA BARDHAMAN | Raina-I | Burdwan Division | RASUIKHANDA PIPED WATER SUPPLY SCHEME | SM/16253 | New | Balance work [i.e. Extension or parallel Pipeline, Leftout FHTC, Road Restoration work, Sinking of Additional Tube Well with Pump House & Boundary wall, inter Connection of Additional Tube Well, Construction of M.S.Structural bridge, canal Crossing, MS casing with allied work of Bhagabatipur, Machkhara, Udgara, Bantir, Chakpurohit Rasuikhanda, Sankarpur, Gopalpur & Belshar PWSS Block-RAINA- I under Burdwan Sub Division, PHE Dte. within Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001103/2024-2025 | 469/BWD | 24/01/2025 | 01/04/2027 | SK ALIM | 1353.91 | 0 | 0 | 55
11 | PURBA BARDHAMAN | Raina-I | Burdwan Division | RASUIKHANDA PIPED WATER SUPPLY SCHEME | SM/16253 | New | Material Requisition To Resource Division |  |  | RTOR000082/2024-2025 | 408/BWD | 17/01/2025 | 17/01/2025 | Resource Division | 7.35 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Raina-I | Central Mechanical | RASUIKHANDA PIPED WATER SUPPLY SCHEME | SM/16253 | New | WBSEDCL Quotation for new service connection at Rasuikhanda water supply scheme, P/H no.-III. |  |  | BILL/00129/2025-2026 |  | 28/04/2025 | 28/04/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.2 | 0 | 0 | 0
Total | [13 empty] | 2600.49 | 630.58 | 24.25