## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina-I | Burdwan Division | RASUIKHANDA PIPED WATER SUPPLY SCHEME | SM/16253 | New | Material Requisition To Resource Division |  |  | RTOR000184/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 7.15 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Raina-I | Burdwan Division | RASUIKHANDA PIPED WATER SUPPLY SCHEME | SM/16253 | New | Material Requisition To Resource Division |  |  | RTOR000484/2023-2024 | 4008/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 2.23 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Raina-I | Burdwan Division | RASUIKHANDA PIPED WATER SUPPLY SCHEME | SM/16253 | New | Material Requisition To Resource Division |  |  | RTOR000688/2023-2024 | 5065/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina-I | Central Mechanical | RASUIKHANDA PIPED WATER SUPPLY SCHEME | SM/16253 | New | New service connection charges for Rasuikhanda PWSS TW-2 |  |  | BILL/01426/2023-2024 | BP-2023-24-153 | 05/09/2023 | 05/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.7 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina-I | Central Mechanical | RASUIKHANDA PIPED WATER SUPPLY SCHEME | SM/16253 | New | New service connection charges for Rasuikhanda PWSS TW 1 |  |  | BILL/01371/2023-2024 | BP-2023-24-139 | 25/08/2023 | 25/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.04 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina-I | Burdwan Division | RASUIKHANDA PIPED WATER SUPPLY SCHEME | SM/16253 | New | Continuation order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte for the period of 01.12.2023 to 31.05.2024 | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001007/2023-2024 | 2751/BSD | 28/11/2023 | 29/05/2024 | SK.ASFIA | 2.4 | 0.4 | 16.65 | 70
7 | PURBA BARDHAMAN | Raina-I | Central Mechanical | RASUIKHANDA PIPED WATER SUPPLY SCHEME | SM/16253 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 25/11/2024 | DEY ENTERPRISE | 74.58 | 0 | 0 | 10
8 | PURBA BARDHAMAN | Raina-I | Burdwan Division | RASUIKHANDA PIPED WATER SUPPLY SCHEME | SM/16253 | New | Balance work [i.e. Extension or parallel Pipeline, Leftout FHTC, Road Restoration work, Sinking of Additional Tube Well with Pump House & Boundary wall, inter Connection of Additional Tube Well, Construction of M.S.Structural bridge, canal Crossing, MS casing with allied work of Bhagabatipur, Machkhara, Udgara, Bantir, Chakpurohit Rasuikhanda, Sankarpur, Gopalpur & Belshar PWSS Block-RAINA- I under Burdwan Sub Division, PHE Dte. within Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001103/2024-2025 | 469/BWD | 24/01/2025 | 25/01/2026 | SK ALIM | 1353.91 | 0 | 0 | 25
Total | [13 empty] | 1479.46 | 0.4 | 0.03