## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina-I | Burdwan Division | UCHITPUR PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/16254 | New | UCHITPUR Single Village Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Raina-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000789/2022-2023 | 1422/BWD | 24/03/2023 | 22/06/2023 | ANWESHA CONSTRUCTION | 77.19 | 0 | 0 | 100
2 | PURBA BARDHAMAN | Raina-I | Burdwan Division | UCHITPUR PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/16254 | New | Material Requisition To Resource Division |  |  | RTOR000422/2023-2024 | 3839/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 1.31 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Raina-I | Burdwan Division | UCHITPUR PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/16254 | New | Material Requisition To Resource Division |  |  | RTOR000698/2023-2024 | 5068/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina-I | Central Mechanical | UCHITPUR PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/16254 | New | New service connection charges for Uchitpur PWSS TW-1 |  |  | BILL/00776/2023-2024 | BP-2023-24-79 | 24/07/2023 | 24/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.26 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina-I | Burdwan Division | UCHITPUR PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/16254 | New | Extension of pipeline & installation of Air Valve for providing FHTC at Dharapara & Malick para of Uchitpur village for UCHITPUR Piped Water Supply Scheme[New Scheme], Block- Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001171/2023-2024 | 530/BSD | 14/03/2024 | 13/04/2024 | ANWESHA CONSTRUCTION | 0.96 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina-I | Burdwan Division | UCHITPUR PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/16254 | New | Providing FHTC at leftour part of Malik Para of Uchitpur Village under UCHITPUR Piped Water Supply Scheme, Block- Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001037/2023-2024 | 281/BSD | 09/02/2024 | 10/03/2024 | ANWESHA CONSTRUCTION | 0.95 | 0 | 0 | 100
7 | PURBA BARDHAMAN | Raina-I | Burdwan Division | UCHITPUR PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/16254 | New | Providing FHTC at leftour part of Dhara Para of Uchitpur Village under UCHITPUR Piped Water Supply Scheme, Block- Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001094/2023-2024 | 518/BSD | 13/03/2024 | 12/04/2024 | ANWESHA CONSTRUCTION | 0.95 | 0 | 0 | 100
8 | PURBA BARDHAMAN | Raina-I | Central Mechanical | UCHITPUR PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/16254 | New | Supply and Delivery of standby pump motor set for Sipta, Uchitpur, Haripur & others Water Supply Scheme under CMD, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000142/2024-2025 | 2596/CMD | 27/08/2024 | 26/09/2024 | JOYGURU ENTERPRISE | 4.72 | 0 | 0 | 100
9 | PURBA BARDHAMAN | Raina-I | Central Mechanical | UCHITPUR PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/16254 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Uchitpur Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000146/2023-2024 | 2881/CMD | 07/07/2023 | 02/06/2024 | WEST BENGAL ENGINEERING CO. | 28.96 | 0 | 0 | 100
10 | PURBA BARDHAMAN | Raina-I | Central Mechanical | UCHITPUR PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/16254 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 25/11/2024 | DEY ENTERPRISE | 74.58 | 0 | 0 | 10
Total | [13 empty] | 216.33 | 0 | 0