## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina-I | Burdwan Division | SHUKUR PIPED WATER SUPPLY SCHEME | SM/16255 | New | Material Requisition To Resource Division |  |  | RTOR000314/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 5.01 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Raina-I | Burdwan Division | SHUKUR PIPED WATER SUPPLY SCHEME | SM/16255 | New | Material Requisition To Resource Division |  |  | RTOR000480/2023-2024 | 4004/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 7.71 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Raina-I | Burdwan Division | SHUKUR PIPED WATER SUPPLY SCHEME | SM/16255 | New | Material Requisition To Resource Division |  |  | RTOR000693/2023-2024 | 5072/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina-I | Central Mechanical | SHUKUR PIPED WATER SUPPLY SCHEME | SM/16255 | New | New service connection charges for Shukur PWSS TW-2 |  |  | BILL/01762/2023-2024 | BP-2023-24-272 | 15/12/2023 | 15/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.71 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina-I | Central Mechanical | SHUKUR PIPED WATER SUPPLY SCHEME | SM/16255 | New | Continuation order-Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven ) for supervision of site for the office of the Assistant Engineer,under CMD,PHE,Dte. [W.e.f-01/10/2024 to 30/11/2024) [UNDER JJM WORKS] | ASSISTANT ENGINEER | Junior Engineer | ORD/000425/2024-2025 | 1248/CMSD | 30/09/2024 | 30/11/2024 | PRODYUT GHOSH | 0.8 | 0.77 | 96.28 | 0
6 | PURBA BARDHAMAN | Raina-I | Central Mechanical | SHUKUR PIPED WATER SUPPLY SCHEME | SM/16255 | New | New Service connection for Sukur W/S Scheme PH No.-I |  |  | BILL/01793/2023-2024 | BP-2023-24-318 | 30/12/2023 | 30/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.06 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina-I | Burdwan Division | SHUKUR PIPED WATER SUPPLY SCHEME | SM/16255 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BAJITPUR, SHUKUR & HARISHNAPUR Piped Water Supply Scheme under RAINA-I Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000388/2023-2024 | 3197/BWD | 24/07/2023 | 23/07/2024 | MRITYUNJOY MUKHERJEE & CO. | 1242.03 | 105.22 | 8.47 | 55
8 | PURBA BARDHAMAN | Raina-I | Burdwan Division | SHUKUR PIPED WATER SUPPLY SCHEME | SM/16255 | New | Continuation Work Order for supply of inspection Vehicle No. WB42Y- 7403 for inspection of different JJM related(schemes) works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub Division under Burdwan Division, PHE Dte consider 96.00 Km. run per day (Period from 01-02-2025 to 30-04-2025) |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001402/2024-2025 | 240/BSD | 31/01/2025 | 07/04/2025 | PARVIN BEGAM | 0.85 | 0.28 | 33.33 | 100
Total | [13 empty] | 1287.62 | 106.27 | 8.25