## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | JHAMATPUR PIPED WATER SUPPLY SCHEME | SM/16256 | New | Material Requisition To Resource Division |  |  | RTOR000059/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 1.42 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | JHAMATPUR PIPED WATER SUPPLY SCHEME | SM/16256 | New | Material Requisition To Resource Division |  |  | RTOR000293/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 2.35 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | JHAMATPUR PIPED WATER SUPPLY SCHEME | SM/16256 | New | Material Requisition To Resource Division |  |  | RTOR000594/2023-2024 | 4902/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 10 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | JHAMATPUR PIPED WATER SUPPLY SCHEME | SM/16256 | New | New service connection charges for Jhamatpur PWSS Tw-1 |  |  | BILL/00761/2023-2024 | BP-2023-24-63 | 18/07/2023 | 18/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.3 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | JHAMATPUR PIPED WATER SUPPLY SCHEME | SM/16256 | New | JHAMATPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000134/2023-2024 | 2384/BWD | 23/05/2023 | 18/03/2024 | M/S M.M. ENTERPRISE | 228.72 | 0 | 0 | 80
6 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | JHAMATPUR PIPED WATER SUPPLY SCHEME | SM/16256 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Kankurhati & others water supply scheme under Ketugram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000103/2024-2025 | 2408/CMD | 02/08/2024 | 31/10/2024 | DIPALI CONSTRUCTION | 41.95 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | JHAMATPUR PIPED WATER SUPPLY SCHEME | SM/16256 | New | New service connection charges for Jhamatpur PWSS TW-2 |  |  | BILL/01899/2023-2024 | BP-2023-24-369 | 15/01/2024 | 15/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.3 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | JHAMATPUR PIPED WATER SUPPLY SCHEME | SM/16256 | New | Supplimentary Quotation for ROW at Jhamatpur PWSS TW-2. |  |  | BILL/00254/2024-2025 | BP-2024-25-132 | 05/06/2024 | 05/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.71 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | JHAMATPUR PIPED WATER SUPPLY SCHEME | SM/16256 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at JHAMATPUR Water Supply Scheme [Block - KETUGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000161/2023-2024 | 2887/CMD | 10/07/2023 | 09/07/2025 | A.S. ENTERPRISE | 20.76 | 0 | 0 | 40
Total | [13 empty] | 312.5 | 0 | 0