## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | DWARIATAN PIPED WATER SUPPLY SCHEME | SM/16285 | New | Material Requisition To Resource Division |  |  | RTOR000078/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 33.94 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | DWARIATAN PIPED WATER SUPPLY SCHEME | SM/16285 | New | Material Requisition To Resource Division |  |  | RTOR000246/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 21.09 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | DWARIATAN PIPED WATER SUPPLY SCHEME | SM/16285 | New | Work Order "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR DWARIATON PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001152/2023-2024 | 2021/KSD | 06/03/2024 | 16/03/2024 | BISWAS ENTERPRISE | 0.66 | 0.66 | 99.78 | 2
4 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | DWARIATAN PIPED WATER SUPPLY SCHEME | SM/16285 | New | New Service connection at Dwariatan PWSS PH-1 |  |  | BILL/02320/2023-2024 | BP-2023-24-459 | 30/01/2024 | 30/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.24 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | DWARIATAN PIPED WATER SUPPLY SCHEME | SM/16285 | New | New electric connection for Dwariatan PWSS, PH-2. |  |  | BILL/01881/2023-2024 | BP-2023-24-353 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.95 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | DWARIATAN PIPED WATER SUPPLY SCHEME | SM/16285 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BALINDAR, CHAK SHIMLA & DWARIATAN Piped Water Supply Scheme under Kalna II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000539/2023-2024 | 3700/BWD | 24/08/2023 | 02/10/2025 | SUPRITI ENTERPRISE | 1424.22 | 29.87 | 2.1 | 30
7 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | DWARIATAN PIPED WATER SUPPLY SCHEME | SM/16285 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at DWARIATAN Water Supply Scheme [ Block- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001053/2023-2024 | 4160/CMD | 29/08/2023 | 31/08/2025 | M/S, S.S. ENTERPRISE. | 28.48 | 15.29 | 53.69 | 40
8 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | DWARIATAN PIPED WATER SUPPLY SCHEME | SM/16285 | New | Different types of works involve in connection with Augmentation of TEHATA Zone-I & II (SM/16301) Water Supply Scheme, CHAKSIMLA (SM/15586) Water Supply Scheme & DWARIATON (SM/16285) Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER RWS KALNA2 | ORD/000162/2024-2025 | 2201/BWD | 13/06/2024 | 05/07/2026 | M/S ASHA CONSTRUCTION | 449.98 | 64.42 | 14.32 | 25
Total | [13 empty] | 1969.55 | 110.23 | 5.6