## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | BIRUHA PIPED WATER SUPPLY SCHEME | SM/16287 | New | Material Requisition To Resource Division |  |  | RTOR000070/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 12.79 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | BIRUHA PIPED WATER SUPPLY SCHEME | SM/16287 | New | Material Requisition To Resource Division |  |  | RTOR000263/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 17.53 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | BIRUHA PIPED WATER SUPPLY SCHEME | SM/16287 | New | Material Requisition To Resource Division |  |  | RTOR000608/2023-2024 | 4913/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 35.77 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | BIRUHA PIPED WATER SUPPLY SCHEME | SM/16287 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AKALPAUSH & BIRUHA Piped Water Supply Scheme under Kalna ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000542/2023-2024 | 3698/BWD | 24/08/2023 | 23/08/2024 | SUPRITI ENTERPRISE | 1010.87 | 0 | 0 | 37
5 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | BIRUHA PIPED WATER SUPPLY SCHEME | SM/16287 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR BIRUHA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001147/2023-2024 | 2096/KSD | 04/03/2024 | 14/03/2024 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0 | 0 | 2
6 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | BIRUHA PIPED WATER SUPPLY SCHEME | SM/16287 | New | New electric connection for Biruha PWSS, PH-1. |  |  | BILL/01870/2023-2024 | BP-2023-24-354 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | BIRUHA PIPED WATER SUPPLY SCHEME | SM/16287 | New | New electric connection for Biruha PWSS, PH-2. |  |  | BILL/01871/2023-2024 | BP-2023-24-355 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.94 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | BIRUHA PIPED WATER SUPPLY SCHEME | SM/16287 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000116/2024-2025 | 2393/CMD | 02/08/2024 | 09/05/2025 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 0 | 20
9 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | BIRUHA PIPED WATER SUPPLY SCHEME | SM/16287 | New | Work order for "Restoration of pipeline with other allied works at different places of Bardalia,Masidpur,Biruha,Mainagari mouja under Birhua Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-II panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000860/2024-2025 | 1845/KSD | 27/11/2024 | 12/12/2024 | SUPRITI ENTERPRISE | 2.89 | 0 | 0 | 100
10 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | BIRUHA PIPED WATER SUPPLY SCHEME | SM/16287 | New | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001270/2024-2025 | 849/BWD | 05/03/2025 | 01/09/2025 | S.P. CONSTRUCTION | 683.3 | 0 | 0 | 0
Total | [13 empty] | 1851.56 | 0 | 0