## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF MANIKHAR PIPED WATER SUPPLY SCHEME PART-C | SM/16289 | Retrofitting | Augmentation of MANIKHAR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Kalna - I Block, Purba Burdwan District under Burdwan Division, PHE. Dte. | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000157/2023-2024 | 2453/BWD | 31/05/2023 | 30/07/2023 | SETH ENTERPRISE | 34.49 | 34.32 | 99.49 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF MANIKHAR PIPED WATER SUPPLY SCHEME PART-C | SM/16289 | Retrofitting | Work Oder for "Laying of Rising Main and alied work such as brick work, P.C.C. work and dismantling work etc. for Manikhar Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000978/2023-2024 | 1706/KSD | 01/12/2023 | 08/12/2023 | BISWAS ENTERPRISE | 0.51 | 0.47 | 91.44 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF MANIKHAR PIPED WATER SUPPLY SCHEME PART-C | SM/16289 | Retrofitting | Arrangement of drinking water supply by installation of solar submersible pump including sinking of 200 mm. dia. Tube well 150 Mtr. Deep by direct rotary rig method, Laying dist. System, FHTC and 2 Nos. 5000 Ltr. PVC tank installation with construction of RCC structure for BHAGABATITALA Habitation which is uncovered of MANIKHAR Piped W/S. Scheme, Block KALNA-1 under Burdwan Division, PHE Dte. | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000018/2025-2026 | 1245/BWD | 23/04/2025 | 07/06/2025 | A.R. TRADERS | 30.74 | 0 | 0 | 75
4 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF MANIKHAR PIPED WATER SUPPLY SCHEME PART-C | SM/16289 | Retrofitting | Work order for 'Restoration of Concrete work and land development at Head Work Site of Manikhar PWSS under Kalna Sub-Division under Burdwan Division, PHE Dte.'. | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000807/2024-2025 | 1771/KSD | 20/11/2024 | 20/12/2024 | BISWAS ENTERPRISE | 3.26 | 0.96 | 29.27 | 100
Total | [13 empty] | 69.01 | 35.74 | 51.79