## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF MAJHERGRAM PIPED WATER SUPPLY SCHEME(PART-B) | SM/16290 | Retrofitting | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for 2nd TW Site of Aug. of MAJHERGRAM & its adjoining mouzas Piped Water Supply Scheme, Block Monteswar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000542/2022-2023 | 5094/BWD | 17/11/2022 | 17/12/2022 | DAS CONSTRUCTION | 8.71 | 7.77 | 89.22 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF MAJHERGRAM PIPED WATER SUPPLY SCHEME(PART-B) | SM/16290 | Retrofitting | Interconnection in distribution system from OHR to in between 1st and 2nd Tube Well site for smooth functioning of FHTC work of MAJHERGRAM W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. |  |  | ORD/000160/2023-2024 | 2575/BWD | 01/06/2023 | 01/07/2023 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD. | 22.54 | 20.07 | 89.06 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF MAJHERGRAM PIPED WATER SUPPLY SCHEME(PART-B) | SM/16290 | Retrofitting | Laying of UPVC pipeline & providing FHTC work at Dhanyakherur, Majhergram bazar & Hattola village of MAJHERGRAM Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000161/2023-2024 | 2456/BWD | 31/05/2023 | 30/06/2023 | PRONAB KUMAR DEY | 9.68 | 5.61 | 57.91 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF MAJHERGRAM PIPED WATER SUPPLY SCHEME(PART-B) | SM/16290 | Retrofitting | Providing FHTC & laying of HDPE pipe line for village of Madhyamgram, Dakshinpara, Binnerpar, Dhanyakherur of MAJHERGRAM PWSS of Manteswer Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000174/2024-2025 | 2251/BWD | 18/06/2024 | 16/10/2024 | A.R. TRADERS | 40.92 | 23.49 | 57.4 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF MAJHERGRAM PIPED WATER SUPPLY SCHEME(PART-B) | SM/16290 | Retrofitting | Laying of 75 mm dia HDPE Pipe of Majhergram PWSS of Madhyamgram uttarpara village under Manteswar Block under Durgapur Sub Division of Burdwan Division ,P.H.E.Dte |  | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000762/2024-2025 | 908/DSD | 28/10/2024 | 27/11/2024 | M/S GOSWAMI CONSTRUCTION | 0.96 | 0.95 | 99.07 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF MAJHERGRAM PIPED WATER SUPPLY SCHEME(PART-B) | SM/16290 | Retrofitting | Painting and others ancillary works related to OHR of MAJHERGRAM PWSS under Durgapur Sub Division of MANTESWER Block under Burdwan Division P.H.E.Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/001221/2024-2025 | 728/BWD | 24/02/2025 | 10/04/2025 | A.R. TRADERS | 7.02 | 0 | 0 | 0
Total | [13 empty] | 89.84 | 57.89 | 64.44