## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF JHAUDANGA (PART-B) PIPED WATER SUPPLY SCHEME | SM/16293 | Augmentation | Construction Pump house and construction (As per drawing no-PHE/SE/CC/PH/DWG-01/ 2022-2023) of new (In same place) Pump House No-2 of JHAUDANGA Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000709/2023-2024 | 4521/BWD | 12/10/2023 | 11/12/2023 | IYASIN DAFADAR | 6.76 | 6.58 | 97.32 | 15
2 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF JHAUDANGA (PART-B) PIPED WATER SUPPLY SCHEME | SM/16293 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of JHAUDANGA( Part-B)[ PURBASTHALI-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001084/2023-2024 | 4475/CMD | 05/10/2023 | 04/11/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 24.19 | 0 | 0 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF JHAUDANGA (PART-B) PIPED WATER SUPPLY SCHEME | SM/16293 | Augmentation | Different types of works involve in connection with Augmentation of JHAUDANGA (SM/16293), KASHIPUR (SM/16297), PATULI (SM/09718) & PARULIA (SM/09719) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000163/2024-2025 | 2202/BWD | 13/06/2024 | 06/03/2026 | MONDAL PRECISION PVT LTD | 570 | 78.03 | 13.69 | 2
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF JHAUDANGA (PART-B) PIPED WATER SUPPLY SCHEME | SM/16293 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for 1ST TW Site of JHAUDANGA & its adjoining mouzas Piped Water Supply Scheme, Block Purbasthali II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000720/2023-2024 | 273/BWD | 16/01/2024 | 15/02/2024 | AUXILIARY TUBE WELL DRILLERS | 8.64 | 7.85 | 90.84 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF JHAUDANGA (PART-B) PIPED WATER SUPPLY SCHEME | SM/16293 | Augmentation | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 09 Nos. Piped W/S. Schemes under Purbasthali II Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000338/2024-2025 | 3018/BWD | 05/08/2024 | 24/09/2024 | HORIZEN | 23.7 | 6.17 | 26.03 | 10
Total | [13 empty] | 633.29 | 98.63 | 15.57