## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF KASHIPUR PIPED WATER SUPPLY SCHEME | SM/16297 | Augmentation | Augmentation of KASHIPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Purbasthali - II Block, Purba Burdwan District under Burdwan Division, PHE.Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000176/2023-2024 | 2588/BWD | 01/06/2023 | 31/07/2023 | BAKSHI ENTERPRISE | 19.74 | 13.85 | 70.18 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF KASHIPUR PIPED WATER SUPPLY SCHEME | SM/16297 | Augmentation | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 09 Nos. Piped W/S. Schemes under Purbasthali II Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000338/2024-2025 | 3018/BWD | 05/08/2024 | 24/09/2024 | HORIZEN | 23.7 | 9.91 | 41.81 | 10
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF KASHIPUR PIPED WATER SUPPLY SCHEME | SM/16297 | Augmentation | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR KASHIPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001166/2023-2024 | 2022/KSD | 06/03/2024 | 16/03/2024 | DEL DELTA CONSTRUCTION | 0.66 | 0.66 | 99.69 | 100
4 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF KASHIPUR PIPED WATER SUPPLY SCHEME | SM/16297 | Augmentation | New service connection charges for Kashipur PWSS TW-1 |  |  | BILL/01866/2023-2024 | BP-2023-24-356 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.77 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF KASHIPUR PIPED WATER SUPPLY SCHEME | SM/16297 | Augmentation | Different types of works involve in connection with Augmentation of JHAUDANGA (SM/16293), KASHIPUR (SM/16297), PATULI (SM/09718) & PARULIA (SM/09719) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000163/2024-2025 | 2202/BWD | 13/06/2024 | 06/03/2026 | MONDAL PRECISION PVT LTD | 570 | 99.42 | 17.44 | 2
6 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF KASHIPUR PIPED WATER SUPPLY SCHEME | SM/16297 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of KASHIPUR[PURBASTHALI-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001080/2023-2024 | 4437/CMD | 01/11/2023 | 01/12/2023 | DUTTA ENTERPRISE | 24.4 | 0 | 0 | 100
Total | [13 empty] | 642.28 | 123.84 | 19.28