## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF NADANGHAT PIPED WATER SUPPLY SCHEME | SM/16298 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of NADANGHAT[PURBASTHALI-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/001082/2023-2024 | 4440/CMD | 04/10/2023 | 03/11/2023 | S.K. ENTERPRISE | 24.39 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF NADANGHAT PIPED WATER SUPPLY SCHEME | SM/16298 | Augmentation | Augmentation of NADANGHAT PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Purbasthali - I Block, Purba Burdwan District under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000077/2023-2024 | 2043/BWD | 03/05/2023 | 02/07/2023 | HAFIJUR RAHAMAN MIDYA | 26.28 | 20.8 | 79.15 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF NADANGHAT PIPED WATER SUPPLY SCHEME | SM/16298 | Augmentation | Laying of Rising Main and distribution system with FHTC work, sinking of tube wells with other allied works in connection with Augmentation of NADANGHAT Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000130/2024-2025 | 2066/BWD | 07/06/2024 | 05/10/2024 | TIRUPATI ENTERPRISES | 272.43 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF NADANGHAT PIPED WATER SUPPLY SCHEME | SM/16298 | Augmentation | Illumination arrangement at Nadanghat water supply scheme under Purbasthali-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000403/2024-2025 | 2782/CMD | 01/10/2024 | 30/11/2024 | SUBRATA BHADRA | 16.18 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF NADANGHAT PIPED WATER SUPPLY SCHEME | SM/16298 | Augmentation | Work Order for "Restoration and laying of HDPE Pipeline at 2nd Pump House adjacent to Dogachhia village of DOGACHHIA PWSS & Nadanghat PWSS (SM/16298) under Kalna Sub-Division under Burdwan Division, PHE Dte.". | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000554/2024-2025 | 774/KSD | 12/07/2024 | 27/07/2024 | HAMID SK | 0.96 | 0.92 | 96.29 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF NADANGHAT PIPED WATER SUPPLY SCHEME | SM/16298 | Augmentation | Work Order for "Restoration and laying of HDPE Pipeline at 2nd Pump House adjacent to Parulia village of PARULIA PWSS & Nadanghat PWSS (SM/16298) under Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000553/2024-2025 | 773/KSD | 12/07/2024 | 27/07/2024 | HAMID SK | 0.96 | 0.96 | 99.96 | 100
7 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF NADANGHAT PIPED WATER SUPPLY SCHEME | SM/16298 | Augmentation | Quotation for load enhancement at Nadanghat PWSS PH 2. |  |  | BILL/00225/2024-2025 | BP-2024-25-116 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.89 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF NADANGHAT PIPED WATER SUPPLY SCHEME | SM/16298 | Augmentation | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001187/2024-2025 | 608/BWD | 11/02/2025 | 07/02/2026 | MANASH GHOSH | 1209.62 | 0 | 0 | 51
Total | [13 empty] | 1551.71 | 22.69 | 1.46