## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF KALYANPUR PIPED WATER SUPPLY SCHEME | SM/16299 | Augmentation | NEW SERVICE CONNECTION FOR AUGMENTATION FOR KALYANPUR PWSS PH-2 |  |  | BILL/00186/2024-2025 | BP-2024-25-87 | 15/05/2024 | 15/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.96 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF KALYANPUR PIPED WATER SUPPLY SCHEME | SM/16299 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of KALYANPUR[KALNA-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001079/2023-2024 | 4438/CMD | 01/11/2023 | 30/11/2025 | SOUNAK ENTERPRISE | 24.41 | 0 | 0 | 50
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF KALYANPUR PIPED WATER SUPPLY SCHEME | SM/16299 | Augmentation | Different types of works involve in connection with Augmentation of KALYANPUR (SM/16299) Water Supply Scheme & BHABANANDAPUR (SM/16024) Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER RWS KALNA2 | ORD/000189/2024-2025 | 2433/BWD | 27/06/2024 | 01/03/2025 | BALAJEE ENTERPRISES | 225.16 | 0 | 0 | 2
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF KALYANPUR PIPED WATER SUPPLY SCHEME | SM/16299 | Augmentation | Providing FHTC work at Kalyanpur village under KALYANPUR Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER RWS KALNA2 | ORD/000885/2023-2024 | 5514/BWD | 14/12/2023 | 13/05/2024 | SETH ENTERPRISE | 13.89 | 0 | 0 | 100
Total | [13 empty] | 269.42 | 0 | 0