## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF KULTI PIPED WATER SUPPLY SCHEME | SM/16301 | Augmentation | Augmentation of KULTI PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Kalna - II Block, Purba Burdwan District under Burdwan Division, PHE.Dte. |  |  | ORD/000588/2023-2024 | 3747/BWD | 28/08/2023 | 27/10/2023 | MAHALAXMI CONSTRUCTION | 21.92 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF KULTI PIPED WATER SUPPLY SCHEME | SM/16301 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1, 2 & 3 at Augmentation of KULTI[KALNA-II]] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/001081/2023-2024 | 4439/CMD | 04/10/2023 | 01/09/2025 | CHOUDHURY ENTERPRISE | 36.64 | 0 | 0 | 33
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF KULTI PIPED WATER SUPPLY SCHEME | SM/16301 | Augmentation | Different types of works involve in connection with Augmentation of KULTI (SM/16301) Water Supply Scheme, Block Kalna II under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER RWS KALNA2 | ORD/000235/2024-2025 | 2553/BWD | 04/07/2024 | 01/03/2025 | HAMID SK | 222.11 | 83.72 | 37.69 | 80
4 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF KULTI PIPED WATER SUPPLY SCHEME | SM/16301 | Augmentation | Illumination arrangement at Kulti water supply scheme under Kalna 2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000407/2024-2025 | 2787/CMD | 01/10/2024 | 31/08/2025 | DELTA ENGINEERING ENTERPRISE | 10.7 | 0 | 0 | 30
5 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF KULTI PIPED WATER SUPPLY SCHEME | SM/16301 | Augmentation | New service connection for augmentation of Kulti PH-3 PWSS. |  |  | BILL/00086/2024-2025 | BP-2024-25-29 | 19/04/2024 | 19/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.7 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF KULTI PIPED WATER SUPPLY SCHEME | SM/16301 | Augmentation | Additional Quotation for augmentation of Kulti PWSS PH 3 |  |  | BILL/00938/2024-2025 | BP-2024-25-407 | 11/12/2024 | 11/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.79 | 0 | 0 | 0
Total | [13 empty] | 297.85 | 83.72 | 28.11