## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | GAHAK PIPE WATER SUPPLY SCHEME | SM/16303 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at GAHAK Water Supply Scheme [ Block- PURBASTHALI -1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [3rd CALL] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000929/2023-2024 | 4192/CMD | 29/08/2023 | 28/09/2023 | SOUNAK ENTERPRISE | 21.33 | 0 | 0 | 50
2 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | GAHAK PIPE WATER SUPPLY SCHEME | SM/16303 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SHYAMPUR, GAHAK & SHANKRA Piped Water Supply Scheme under Purbasthali I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000639/2023-2024 | 3957/BWD | 07/09/2023 | 24/07/2026 | M/S B. NANDI | 758.52 | 92.6 | 12.21 | 20
3 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | GAHAK PIPE WATER SUPPLY SCHEME | SM/16303 | New | Material Requisition To Resource Division |  |  | RTOR000252/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 7.5 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | GAHAK PIPE WATER SUPPLY SCHEME | SM/16303 | New | Material Requisition To Resource Division |  |  | RTOR000591/2023-2024 | 4899/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 15.99 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | GAHAK PIPE WATER SUPPLY SCHEME | SM/16303 | New | Material Requisition To Resource Division |  |  | RTOR000548/2023-2024 | 4308/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 0.81 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | GAHAK PIPE WATER SUPPLY SCHEME | SM/16303 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000714/2024-2025 | 2979/CMD | 25/11/2024 | 23/02/2025 | H.K. DAS & CO. | 53.27 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | GAHAK PIPE WATER SUPPLY SCHEME | SM/16303 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR GAHAK PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000571/2024-2025 | 1017/KSD | 07/08/2024 | 22/08/2024 | DEL DELTA CONSTRUCTION | 0.66 | 0.66 | 99.69 | 100
8 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | GAHAK PIPE WATER SUPPLY SCHEME | SM/16303 | New | New service connection for Gahak PWSS TW-1. |  |  | BILL/02393/2023-2024 | BP-2023-24-497 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.7 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | GAHAK PIPE WATER SUPPLY SCHEME | SM/16303 | New | New service connection for Gahak PWSS TW-2. |  |  | BILL/02392/2023-2024 | BP-2023-24-498 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.7 | 0 | 0 | 0
Total | [13 empty] | 867.47 | 93.26 | 10.75