## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF BAMANGARIA PIPED WATER SUPPLY SCHEME | SM/16304 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of BAMUNGARIA[PURBASTHALI-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/001077/2023-2024 | 4201/CMD | 29/08/2023 | 28/09/2023 | DAS TRADING CO. | 24.41 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF BAMANGARIA PIPED WATER SUPPLY SCHEME | SM/16304 | Augmentation | Augmentation of BAMANGARIA PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Purbasthali - I Block, Purba Burdwan District under Burdwan Division, PHE.Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000076/2023-2024 | 2044/BWD | 03/05/2023 | 02/07/2023 | TAPAS KUMAR ROY | 38.28 | 0 | 0 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF BAMANGARIA PIPED WATER SUPPLY SCHEME | SM/16304 | Augmentation | Construction of 350cum OHR & Other Allied Works in connection with Augmentation of (SM/07803), (SM/09410), (SM/16304), (SM/15172) & (SM/14020) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001048/2024-2025 | 220/BWD | 10/01/2025 | 07/10/2025 | R.K. MANDAL& CO. | 491.79 | 0 | 0 | 1
Total | [13 empty] | 554.49 | 0 | 0