## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF RAHATPUR PIPED WATER SUPPLY SCHEME | SM/16306 | Augmentation | Different Types of work involved in connection with Augmentation of RAHATPUR (SM/16306) & LAKSHMANPUR (SM/13493) Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000176/2024-2025 | 2069/BWD | 07/06/2024 | 02/02/2025 | SAIKAT RAY | 213.73 | 0 | 0 | 2
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF RAHATPUR PIPED WATER SUPPLY SCHEME | SM/16306 | Augmentation | Augmentation of RAHATPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Purbasthali - I Block, Purba Burdwan District under Burdwan Division, PHE. Dte. |  |  | ORD/000084/2023-2024 | 2114/BWD | 10/05/2023 | 09/07/2023 | BARDHAMAN AQUA ENGINEERING | 18.67 | 17.56 | 94.02 | 100
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF RAHATPUR PIPED WATER SUPPLY SCHEME | SM/16306 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of RAHATPUR[PURBASTHALI-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001083/2023-2024 | 4474/CMD | 05/10/2023 | 07/05/2025 | S.K. ELECTRICALS | 23.71 | 0 | 0 | 100
Total | [13 empty] | 256.12 | 17.56 | 6.85