## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE IV | SM/16307 | Augmentation | Augmentation of PURBASTHALI Surface Water Supply Scheme (ZONE-4A) with LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Purbasthali-II Block, District:- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000385/2023-2024 | 3137/BWD | 20/07/2023 | 19/07/2026 | SAKTI ENTERPRISE | 432.83 | 122.14 | 28.22 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE IV | SM/16307 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000518/2023-2024 | 3968/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 28.36 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE IV | SM/16307 | Augmentation | Different types of works involve in connection with Augmentation of KRISHNABATI (SM/07827), PURBASTHLI (SM/07866), SINHARI (SM/09716) & SURFACE based W/S Scheme (SM/15571) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000181/2024-2025 | 2296/BWD | 20/06/2024 | 26/02/2026 | M/S DATTA ENTERPRISE | 579.85 | 0 | 0 | 2
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE IV | SM/16307 | Augmentation | Work Order for "Route Survey & Preparation of DPR for Augmentation of Purbasthali Surface Water Based PWSS Zone-IV (Zone-IV B) (SM/16307) under Kalna Sub-Division under Burdwan Division, PHE Dte." Sl-3 | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001136/2023-2024 | 2071/KSD | 29/02/2024 | 14/04/2024 | APEX ENGINEERING | 2.53 | 0 | 0 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE IV | SM/16307 | Augmentation | Work order for "Route Survey & Preparation of DPR for Augmentation of Purbasthali Surface Water Based PWSS Zone-IV (Zone-IV A) (SM/16307) under Kalna Sub-Division under Burdwan Division, PHE Dte." (SL-5) | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001138/2023-2024 | 2080/KSD | 29/02/2024 | 14/04/2024 | APEX ENGINEERING | 2.27 | 0 | 0 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE IV | SM/16307 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000764/2023-2024 | 203/BWD | 10/01/2024 | 10/01/2024 | Resource Division | 6.16 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE IV | SM/16307 | Augmentation | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001187/2024-2025 | 608/BWD | 11/02/2025 | 07/02/2026 | MANASH GHOSH | 1209.62 | 0 | 0 | 51
Total | [13 empty] | 2261.62 | 122.14 | 5.4