## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | SADHPUKHARIA PIPED WATER SUPPLY SCHEME | SM/16308 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at SADHPUKHRIA Water Supply Scheme [ Block- KALNA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [2nd CALL] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000864/2023-2024 | 4131/CMD | 29/08/2023 | 28/09/2023 | SIMARR | 20.64 | 9.28 | 44.96 | 71
2 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | SADHPUKHARIA PIPED WATER SUPPLY SCHEME | SM/16308 | New | Work Order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) for the Office of the Assistant Engineer, Kalna Sub-Division, Burdwan Division, P.H.E. Dte. [Period from 01.12.2023 to 31.05.2024] (Vehicle No-WB 25K 4575). | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000982/2023-2024 | 1680/KSD | 22/11/2023 | 23/05/2024 | SUSMITA MANDAL | 0.87 | 2.33 | 267.77 | 23
3 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | SADHPUKHARIA PIPED WATER SUPPLY SCHEME | SM/16308 | New | SADHPUKHARIA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Kalna-II Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000061/2023-2024 | 1934/BWD | 24/04/2023 | 02/03/2024 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 72 | 66.88 | 92.89 | 30
4 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | SADHPUKHARIA PIPED WATER SUPPLY SCHEME | SM/16308 | New | Material Requisition To Resource Division |  |  | RTOR000048/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 1.38 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | SADHPUKHARIA PIPED WATER SUPPLY SCHEME | SM/16308 | New | Material Requisition To Resource Division |  |  | RTOR000185/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 15.09 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | SADHPUKHARIA PIPED WATER SUPPLY SCHEME | SM/16308 | New | Material Requisition To Resource Division |  |  | RTOR000617/2023-2024 | 4884/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 33.21 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | SADHPUKHARIA PIPED WATER SUPPLY SCHEME | SM/16308 | New | New service connection charges for Sadhpukuria PWSS TW-1 |  |  | BILL/01488/2023-2024 | BP-2023-24-185 | 04/10/2023 | 04/10/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.37 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | SADHPUKHARIA PIPED WATER SUPPLY SCHEME | SM/16308 | New | Continuation work Order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) for the Office of the Assistant Engineer, Kalna Sub-Division, Burdwan Division, P.H.E. Dte. [Period - 01.06.2024 to 30.11.2024]" (Vehicle No-WB 25K 4575) | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000461/2024-2025 | 273/KSD | 30/05/2024 | 29/11/2024 | SUSMITA MANDAL | 2.4 | 2.25 | 93.84 | 0
9 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | SADHPUKHARIA PIPED WATER SUPPLY SCHEME | SM/16308 | New | Continuation work order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) for the Office of the Assistant Engineer, Kalna Sub-Division, Burdwan Division, P.H.E. Dte. [Period from 01.12.2024 to 28.02.2025]". [Vehicle No- WB 25K 4575]. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001066/2024-2025 | 1896/KSD | 29/11/2024 | 28/02/2025 | SUSMITA MANDAL | 1.2 | 1.14 | 95.27 | 0
10 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | SADHPUKHARIA PIPED WATER SUPPLY SCHEME | SM/16308 | New | Work order for "DESIGNING,MAKING AND ERECTION OF SIGN BOARD FOR SAJAL GRAM IN ¿¿6 No... VILLAGE, ¿KALNA-II... BLOCK UNDER KALNA SUB DIVISION WITHIN BURDWAN DIVISION PHE DTE.(18nos board)". | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000949/2024-2025 | 1983/KSD | 06/12/2024 | 16/12/2024 | OMKAR ENTERPRISE | 2.52 | 0 | 0 | 100
11 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | SADHPUKHARIA PIPED WATER SUPPLY SCHEME | SM/16308 | New | Work Order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) for the Office of the Assistant Engineer, Kalna Sub-Division, Burdwan Division, P.H.E. Dte. [Period from 01.03.2025 to 31.05.2025]". [Vehicle No- 25 K 4575]. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001243/2024-2025 | 316/KSD | 28/02/2025 | 31/05/2025 | SUSMITA MANDAL | 1.2 | 0.39 | 32.26 | 1
Total | [13 empty] | 153.87 | 82.27 | 53.46