## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF SONARUDRA PIPED WATER SUPPLY SCHEME | SM/16349 | Retrofitting | Augmentation of SONARUDRA PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jivan Mission of Purbasthali - I Block, Purba Burdwan District under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000152/2023-2024 | 2442/BWD | 30/05/2023 | 29/07/2023 | ROHAN MONDAL | 43.32 | 34.66 | 80.02 | 20
2 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF SONARUDRA PIPED WATER SUPPLY SCHEME | SM/16349 | Retrofitting | Sinking of additional Tube Well, construction of pump house & boundary wall & laying interconnection of SONARUDRA Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (PP Site- Shyambati Baidyapur). | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000864/2023-2024 | 5295/BWD | 01/12/2023 | 30/01/2024 | HI-LIGHT ELECTRONICS | 27.37 | 14.41 | 52.66 | 60
3 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF SONARUDRA PIPED WATER SUPPLY SCHEME | SM/16349 | Retrofitting | Laying of 140 mm dia HDPE Pipeline from Sonarudra Head Work Site more to upto Shyambati & Baidyapur more (Sec 34-2-3-6-10-12-14-16-16A-16B) of SONARUDRA W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000601/2021-2022 | 1486/BWD | 14/03/2022 | 13/04/2022 | HAMID SK | 18.85 | 10.47 | 55.51 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF SONARUDRA PIPED WATER SUPPLY SCHEME | SM/16349 | Retrofitting | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 14 Nos. Piped W/S. Schemes under Purbasthali I Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000337/2024-2025 | 3017/BWD | 05/08/2024 | 19/10/2024 | HORIZEN | 38 | 3.24 | 8.53 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF SONARUDRA PIPED WATER SUPPLY SCHEME | SM/16349 | Retrofitting | Different Types of work involved in connection with Augmentation of SONARUDRA (SM/16349) & KACHUA (SM/13497) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000192/2024-2025 | 2430/BWD | 27/06/2024 | 20/10/2025 | R.G. INFRASTRUCTURE | 240.7 | 23.03 | 9.57 | 2
Total | [13 empty] | 368.24 | 85.81 | 23.3