## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram-I | Central Drilling | KHANJI PIPED WATER SUPPLY SCHEME | SM/16476 | New | Providing drilling crew and other allied works or construction of Tube Well (250mm x 200mm x 114 Mtrs. Depth) by utilising Departmental machineries for Khanji Scheme (T/W-i & II) ketugram-I Block under Purba Bardhaman District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000055/2023-2024 | 861/CDD | 10/07/2023 | 09/08/2023 | OSMAN SEKH | 16.66 | 13.26 | 79.57 | 100
2 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | KHANJI PIPED WATER SUPPLY SCHEME | SM/16476 | New | Material Requisition To Resource Division |  |  | RTOR000099/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 5.23 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | KHANJI PIPED WATER SUPPLY SCHEME | SM/16476 | New | Material Requisition To Resource Division |  |  | RTOR000379/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 12.94 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | KHANJI PIPED WATER SUPPLY SCHEME | SM/16476 | New | Material Requisition To Resource Division |  |  | RTOR000748/2023-2024 | 5261/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 20.18 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | KHANJI PIPED WATER SUPPLY SCHEME | SM/16476 | New | New service connection charges for Khanji PWSS TW-2 |  |  | BILL/01665/2023-2024 | BP-2023-24-223 | 10/11/2023 | 10/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.96 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | KHANJI PIPED WATER SUPPLY SCHEME | SM/16476 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 31/10/2024 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | KHANJI PIPED WATER SUPPLY SCHEME | SM/16476 | New | Quotation for new electric service connection at Khanji PWSS TW No-1 |  |  | BILL/01731/2023-2024 | BP-2023-24-270 | 11/12/2023 | 11/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.48 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | KHANJI PIPED WATER SUPPLY SCHEME | SM/16476 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MALGRAM, MURGRAM, MORGRAM & KHANJI Piped Water Supply Scheme under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000435/2023-2024 | 3387/BWD | 03/08/2023 | 01/01/2026 | PUSPA ENTERPRISE | 1333.98 | 242.7 | 18.19 | 40
9 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | KHANJI PIPED WATER SUPPLY SCHEME | SM/16476 | New | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Murgram, Moregram, Malgram, Khanji, PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000289/2024-2025 | 2739/BWD | 12/07/2024 | 01/01/2025 | PUSPA ENTERPRISE | 185.75 | 21.14 | 11.38 | 72
10 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | KHANJI PIPED WATER SUPPLY SCHEME | SM/16476 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-3 at Khanji Water Supply Scheme [ BLOCK- Ketugram-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/001389/2024-2025 | 882/CMD | 26/03/2025 | 25/05/2025 | KAMAKHYA ENTERPRISE | 11.62 | 0 | 0 | 0
Total | [13 empty] | 1676.07 | 277.1 | 16.53