## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | BALINDAR PIPED WATER SUPPLY SCHEME | SM/16478 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BALINDAR, CHAK SHIMLA & DWARIATAN Piped Water Supply Scheme under Kalna II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000539/2023-2024 | 3700/BWD | 24/08/2023 | 02/10/2025 | SUPRITI ENTERPRISE | 1424.22 | 83.43 | 5.86 | 30
2 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | BALINDAR PIPED WATER SUPPLY SCHEME | SM/16478 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BALINDAR Water Supply Scheme [ Block- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000858/2023-2024 | 4126/CMD | 29/08/2023 | 23/09/2025 | ASIA CONSTRUCTION. | 28.98 | 0 | 0 | 90
3 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | BALINDAR PIPED WATER SUPPLY SCHEME | SM/16478 | New | Material Requisition To Resource Division |  |  | RTOR000056/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 45.18 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | BALINDAR PIPED WATER SUPPLY SCHEME | SM/16478 | New | Material Requisition To Resource Division |  |  | RTOR000204/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 11.21 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | BALINDAR PIPED WATER SUPPLY SCHEME | SM/16478 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000116/2024-2025 | 2393/CMD | 02/08/2024 | 09/05/2025 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 0 | 20
6 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | BALINDAR PIPED WATER SUPPLY SCHEME | SM/16478 | New | Work order for "Restoration of pipeline with other allied works at different places of Bharkunda,potna,Bara dhamash,Balindar,Tola mouja under Balindar Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-II panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte.". | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000858/2024-2025 | 1844/KSD | 27/11/2024 | 12/12/2024 | SUPRITI ENTERPRISE | 2.86 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | BALINDAR PIPED WATER SUPPLY SCHEME | SM/16478 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR BALINDAR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001150/2023-2024 | 2106/KSD | 04/03/2024 | 14/03/2024 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0.66 | 99.78 | 2
8 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | BALINDAR PIPED WATER SUPPLY SCHEME | SM/16478 | New | New service connection charges for Balindar PWSS TW-1 |  |  | BILL/01867/2023-2024 | BP-2023-24-357 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.2 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | BALINDAR PIPED WATER SUPPLY SCHEME | SM/16478 | New | New service connection for BALINDAR PWSS TW-2. |  |  | BILL/02401/2023-2024 | BP-2023-24-503 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.97 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | BALINDAR PIPED WATER SUPPLY SCHEME | SM/16478 | New | Construction of Pipe carrying Truss Bridge for carrying 200 mm dia MS Pipe at PWD Bridge under Hatgachha Mouza under the command area of Balindar PWSS (SM/16478) within Kalna -II block of Kalna Sub-Division, PHE Dte under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000017/2025-2026 | 1244/BWD | 23/04/2025 | 22/06/2025 | M/S DATTA ENTERPRISE | 29.3 | 0 | 0 | 1
11 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | BALINDAR PIPED WATER SUPPLY SCHEME | SM/16478 | New | Providing of Balance FHTC and other allied works at Baradhamas Mouza under the command area of Balindar Piped Water Supply Scheme (SM/16478) in order to declare Sajalgram under Kalna-II Block under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000021/2025-2026 | 1248/BWD | 23/04/2025 | 01/07/2025 | GOPINATH ENTERPRISE | 13.68 | 0 | 0 | 100
12 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | BALINDAR PIPED WATER SUPPLY SCHEME | SM/16478 | New | Providing of Balance FHTC and other allied works at Bhurkunda & Balindar Mouza under the command area of Balindar Piped Water Supply Scheme (SM/16478) in order to declare Sajalgram under Kalna-II Block under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000023/2025-2026 | 1250/BWD | 23/04/2025 | 01/07/2025 | GOPINATH ENTERPRISE | 12.19 | 0 | 0 | 100
13 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | BALINDAR PIPED WATER SUPPLY SCHEME | SM/16478 | New | Providing of Balance FHTC and other allied works at Tola Mouza under the command area of Balindar Piped Water Supply Scheme (SM/16478) in order to declare Sajalgram under Kalna-II Block under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000019/2025-2026 | 1246/BWD | 23/04/2025 | 01/07/2025 | GOPINATH ENTERPRISE | 15.44 | 0 | 0 | 100
14 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | BALINDAR PIPED WATER SUPPLY SCHEME | SM/16478 | New | Material Requisition To Resource Division |  |  | RTOR000040/2024-2025 | 320/BWD | 15/01/2025 | 15/01/2025 | Resource Division | 4.26 | 0 | 0 | 0
Total | [13 empty] | 1677.95 | 84.08 | 5.01