## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH | SM/16479 | Augmentation | Continuation for the work of Supply of one No. Diesel Driven Car (other than Ambasader) on hire basis for the office of the Assistant Engineer, RWS Burdwan Sub-Division, PHE Dte. (Period from 01-11-2024 to 31-12-2024). | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Contractual Junior Engineer | ORD/000763/2024-2025 | 352/RWS | 30/10/2024 | 30/12/2024 | MD HASIN | 0.8 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH | SM/16479 | Augmentation | Illumination arrangement & different electro-mechanical works at SAKTIGARH water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000479/2024-2025 | 2956/CMD | 20/11/2024 | 19/01/2025 | CHOUDHURY ENTERPRISE | 14.34 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH | SM/16479 | Augmentation | Continuation for the work of Supply of one No. Diesel Driven Car ( other than Ambasader) on hire basis for the office of the Assistant Engineer, RWS Burdwan Sub-Division, PHE Dte. (Period from 01-09-2024 to 31-10-2024). |  | Contractual Junior Engineer | ORD/000561/2024-2025 | 274/RWS | 30/08/2024 | 30/10/2024 | MD HASIN | 0.8 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH | SM/16479 | Augmentation | Supply of one No. Diesel Driven Car ( other than Ambasader) on hire basis for the office of the Assistant Engineer, RWS Burdwan Sub-Division, PHE Dte. (Period from 01-07-2024 to 31-08-2024). |  | Contractual Junior Engineer | ORD/000364/2024-2025 | 207/RWS | 28/06/2024 | 28/08/2024 | MD HASIN | 0.8 | 0.57 | 70.67 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH | SM/16479 | Augmentation | Continuation Work for the supply of one no. Diesel driven Motor Cab/Maxi Cab (Air Conditioner) on hire basis for the office of the Assistant Engineer, to be used by the Assistant Engineer, RWS Burdwan Sub-Divn., PHE. Dte. (Period from 01/01/2024 to 29/02/2024) |  | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001221/2023-2024 | 403/RWS | 29/12/2023 | 29/02/2024 | MD HASIN | 0.8 | 0.5 | 62.87 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH | SM/16479 | Augmentation | Protection work of LDS and approach road to 2nd Pump-House of Saktigarh PWSS Augmentation at the node point of 161-166 under Burdwan Division, PHE Dte. [SM-16479] |  | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001170/2023-2024 | 94/RWS | 13/03/2024 | 02/04/2024 | JAYANTA CHAKRABORTY | 0.95 | 0.95 | 99.81 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH | SM/16479 | Augmentation | Crossing of Old G.T Road near Head Works with 250 mm dia pipeline through pushing of 750mm.dia RCC casing pipe by hydraulic jacking method for Saktigarh W/S Scheme (Augmentation) under Burdwan Division, PHE Dte. |  | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000083/2024-2025 | 153/RWS | 29/04/2024 | 24/05/2024 | IJABUL SEKH | 6.55 | 6.55 | 100 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH | SM/16479 | Augmentation | Protection of LDS of Saktigarh PWSS Augmentation at the node point of 36-44-64 under Burdwan Division, PHE Dte. [SM-16479] |  | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001168/2023-2024 | 92/RWS | 13/03/2024 | 02/04/2024 | KHUSI BHAKAT | 0.78 | 0.76 | 98.34 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH | SM/16479 | Augmentation | Protection of LDS of Saktigarh PWSS Augmentation at the node point of 75-123 under Burdwan Division, PHE Dte. [SM-16479] |  | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001169/2023-2024 | 93/RWS | 13/03/2024 | 02/04/2024 | GHOSH ENTERPRISE | 0.79 | 0.79 | 99.84 | 100
10 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH | SM/16479 | Augmentation | Quotation for new service connection at Augmentation of Shaktigarh W/S Scheme TW-3. |  |  | BILL/00372/2024-2025 | BP-2024-25-184 | 08/07/2024 | 08/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.01 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH | SM/16479 | Augmentation | Additional quotation for conversion of HTOH line from HT at Saktigarh (Aug) PWSS. |  |  | BILL/00442/2024-2025 | BP-2024-25-231 | 30/07/2024 | 30/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.08 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH | SM/16479 | Augmentation | Quotation for new service connection for Shaktigarh PWSS PH-2 |  |  | BILL/00294/2024-2025 | BP-2024-25-183 | 08/07/2024 | 08/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.48 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH | SM/16479 | Augmentation | Continuation for the work of Supply of one No. Diesel Driven Car (other than Ambasader) on hire basis for the office of the Assistant Engineer, RWS Burdwan Sub-Division, PHE Dte. (Period from 01-01-2025 to 28-02-2025). | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Contractual Junior Engineer | ORD/000995/2024-2025 | 413/RWS | 31/12/2024 | 28/02/2025 | MD HASIN | 0.79 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH | SM/16479 | Augmentation | Continuation for the work of Supply of one No. Diesel Driven Car (other than Ambasader) on hire basis for the office of the Assistant Engineer, RWS Burdwan Sub-Division, PHE Dte. (Period from 01-05-2025 to 30-06-2025) | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Contractual Junior Engineer | ORD/000045/2025-2026 | 113/RWS | 30/04/2025 | 30/06/2025 | MD HASIN | 0.8 | 0 | 0 | 0
15 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH | SM/16479 | Augmentation | Upgradation of Boundary wall, Drain & land development at Head work site for SHAKTIGAR PWSS under Burdwan-Sub Div, Block-Burdwan II under Burdwan Div. PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000051/2025-2026 | 1425/BWD | 20/05/2025 | 19/06/2025 | SARKAR AGENCY | 5.39 | 0 | 0 | 0
16 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH | SM/16479 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Saktigrah Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000098/2023-2024 | 2587/CMD | 07/06/2023 | 01/07/2025 | P.K. ENGINEERING | 22.69 | 0 | 0 | 100
Total | [13 empty] | 72.83 | 10.12 | 13.9