## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | ARGUN PIPED WATER SUPPLY SCHEME | SM/16482 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMEGERIA, ARGUN, CHINISPUR & KULUTIA Piped Water Supply Scheme under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000533/2023-2024 | 3630/BWD | 21/08/2023 | 01/09/2026 | M/S GOUTAM DAS | 1421.7 | 240.73 | 16.93 | 75
2 | PURBA BARDHAMAN | Ketugram-I | Central Drilling | ARGUN PIPED WATER SUPPLY SCHEME | SM/16482 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Argun W/S Scheme (T/W-I & II) , Ketugram-I Block under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000171/2023-2024 | 1056/CDD | 16/08/2023 | 15/09/2023 | C.M. ENTERPRISE | 16.2 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | ARGUN PIPED WATER SUPPLY SCHEME | SM/16482 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at ARGUN Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000845/2023-2024 | 4119/CMD | 29/08/2023 | 28/09/2023 | DUTTA ENTERPRISE | 26.95 | 20.79 | 77.15 | 88
4 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | ARGUN PIPED WATER SUPPLY SCHEME | SM/16482 | New | Material Requisition To Resource Division |  |  | RTOR000095/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 2.38 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | ARGUN PIPED WATER SUPPLY SCHEME | SM/16482 | New | Material Requisition To Resource Division |  |  | RTOR000212/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 16.15 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | ARGUN PIPED WATER SUPPLY SCHEME | SM/16482 | New | Material Requisition To Resource Division |  |  | RTOR000742/2023-2024 | 5253/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 20.18 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | ARGUN PIPED WATER SUPPLY SCHEME | SM/16482 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 31/10/2024 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | ARGUN PIPED WATER SUPPLY SCHEME | SM/16482 | New | New Service connection for Argun PWSS TW-1 |  |  | BILL/02349/2023-2024 | BP-2023-24-460 | 30/01/2024 | 30/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.91 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | ARGUN PIPED WATER SUPPLY SCHEME | SM/16482 | New | New Service connection at Argun PWSS PH-2 |  |  | BILL/02344/2023-2024 | BP-2023-24-461 | 30/01/2024 | 30/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.63 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | ARGUN PIPED WATER SUPPLY SCHEME | SM/16482 | New | Hiring of one no Diesel Motor Cab (BS-VI) including the cost of fuel . mobile & other charges for the inspection of the different projects of JJM for the office of the Assistant Engineer, Katwa Sub-Division, PHE Dte. (Period:- 01/03/2025 to 31/08/2025) [Sl No-02] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/001324/2024-2025 | 321/KTS | 28/02/2025 | 31/08/2025 | HAMID SK | 1.84 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | ARGUN PIPED WATER SUPPLY SCHEME | SM/16482 | New | Operation of Distribution System , Rising main, Sluice Valves, including operation of sluice valves of ARGUN PWSS under Ketugram-I Block within Katwa Sub-Division under Burdwan Division, PHE Dte. [Period for 03(Three) Months ] [Period 01.01.2026 to 31.03.2026][SL No-04] | Assistant Engineer |  | ORD/001319/2025-2026 | 2237/KTS | 31/12/2025 | 31/03/2026 | DULU MIDDA | 0.65 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | ARGUN PIPED WATER SUPPLY SCHEME | SM/16482 | New | Road crossing through metal / concrete road by Jack Push Method for AMEGERIA (SM/16023), ARGUN (SM/16482), CHINISPUR (SM/15170) and KULITIA (SM/15167) PWSS under Ketugram I Development Block under Katwa Sub Division within Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/001311/2024-2025 | 977/BWD | 13/03/2025 | 12/05/2025 | M/S GOUTAM DAS | 39.22 | 0 | 0 | 100
Total | [13 empty] | 1638.1 | 261.52 | 15.96