## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | BANKAPASI PIPE WATER SUPPLY SCHEME | SM/16484 | New | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 4.03 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | BANKAPASI PIPE WATER SUPPLY SCHEME | SM/16484 | New | Material Requisition To Resource Division |  |  | RTOR000229/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 11.91 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | BANKAPASI PIPE WATER SUPPLY SCHEME | SM/16484 | New | Material Requisition To Resource Division |  |  | RTOR000559/2023-2024 | 4892/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 27.17 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | BANKAPASI PIPE WATER SUPPLY SCHEME | SM/16484 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 25/11/2024 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | BANKAPASI PIPE WATER SUPPLY SCHEME | SM/16484 | New | Continuation Work Order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000107/2024-2025 | 485/KTS | 16/04/2024 | 27/06/2024 | AJIT SAMANTA | 0.92 | 0.23 | 25 | 10
6 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | BANKAPASI PIPE WATER SUPPLY SCHEME | SM/16484 | New | NEW SERVICE CONNECTION FOR BANKAPASI PWSS. |  |  | BILL/02862/2023-2024 | BP-2023-24-613 | 06/03/2024 | 06/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.89 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | BANKAPASI PIPE WATER SUPPLY SCHEME | SM/16484 | New | NEW SERVICE CONNECTION FOR BANKAPASI PWSS TW- 2. |  |  | BILL/02864/2023-2024 | BP-2023-24-614 | 06/03/2024 | 06/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.23 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | BANKAPASI PIPE WATER SUPPLY SCHEME | SM/16484 | New | BANKAPASI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mongolkote Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000501/2023-2024 | 3534/BWD | 10/08/2023 | 01/10/2025 | DESTINATION SOLUTIONS & SERVICES PRIVATE LIMITED | 490.18 | 99.57 | 20.31 | 20
9 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | BANKAPASI PIPE WATER SUPPLY SCHEME | SM/16484 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BANKAPASI Water Supply Scheme [ Block- MANGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000877/2023-2024 | 4140/CMD | 29/08/2023 | 30/05/2025 | CHOUDHURY ENTERPRISE | 28.62 | 0 | 0 | 43
Total | [13 empty] | 638.01 | 99.8 | 15.64