## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | AKALPAUSH PIPE WATER SUPPLY SCHEME | SM/16485 | New | Material Requisition To Resource Division |  |  | RTOR000201/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 20.78 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | AKALPAUSH PIPE WATER SUPPLY SCHEME | SM/16485 | New | Material Requisition To Resource Division |  |  | RTOR000609/2023-2024 | 4914/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 31.31 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | AKALPAUSH PIPE WATER SUPPLY SCHEME | SM/16485 | New | Material Requisition To Resource Division |  |  | RTOR000053/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 34.71 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | AKALPAUSH PIPE WATER SUPPLY SCHEME | SM/16485 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AKALPAUSH & BIRUHA Piped Water Supply Scheme under Kalna ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000542/2023-2024 | 3698/BWD | 24/08/2023 | 23/08/2024 | SUPRITI ENTERPRISE | 1010.87 | 0 | 0 | 37
5 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | AKALPAUSH PIPE WATER SUPPLY SCHEME | SM/16485 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR AKALPOUSH PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001146/2023-2024 | 2095/KSD | 04/03/2024 | 14/03/2024 | BISWAS ENTERPRISE | 0.66 | 0 | 0 | 2
6 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | AKALPAUSH PIPE WATER SUPPLY SCHEME | SM/16485 | New | Material Requisition To Resource Division |  |  | RTOR000783/2023-2024 | 330/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 13.92 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | AKALPAUSH PIPE WATER SUPPLY SCHEME | SM/16485 | New | RESTORATION WORK OF KALNA BAIDYAPUR ROAD TO AKALPOUSH HC ROAD FROM 0.00 KM TO 1.50 KM (IN STRETCHES )DAMAGED DUE TO LAYING OF UNDERGROUND WATER PIPELINEBY PHE WITH BOX CUTTING AND JHAMA WITH MOORUM CONSOLIDATION UNDR KALNA HIGHWAY SUB DIVISION OF BURDWAN SOUTH HIGHWAY DIVISION P.W.(ROADS) DTE.. DURING YEAR 2023-2024. |  |  | BILL/00646/2024-2025 | 825/JJM | 13/09/2024 | 13/09/2024 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 1.85 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | AKALPAUSH PIPE WATER SUPPLY SCHEME | SM/16485 | New | New Service connection at Akalpoush PWSS PH-2 |  |  | BILL/02322/2023-2024 | BP-2023-24-452 | 30/01/2024 | 30/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.25 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | AKALPAUSH PIPE WATER SUPPLY SCHEME | SM/16485 | New | New Service connection at Akalpoush PWSS PH-1 |  |  | BILL/02321/2023-2024 | BP-2023-24-451 | 30/01/2024 | 30/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.42 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | AKALPAUSH PIPE WATER SUPPLY SCHEME | SM/16485 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000116/2024-2025 | 2393/CMD | 02/08/2024 | 09/05/2025 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 0 | 20
11 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | AKALPAUSH PIPE WATER SUPPLY SCHEME | SM/16485 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at AKALPAUSH Water Supply Scheme [ Block-KALNA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [3rd CALL] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001055/2023-2024 | 4190/CMD | 29/08/2023 | 28/09/2023 | AMUSAR IMPEX PVT. LTD. | 28.57 | 0 | 0 | 100
Total | [13 empty] | 1229.15 | 0 | 0