## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF RAYAN (PART-II) PWSS | SM/16486 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Rayan Part - 2 Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000091/2023-2024 | 2595/CMD | 07/06/2023 | 07/07/2023 | P.K. ENGINEERING | 24.2 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF RAYAN (PART-II) PWSS | SM/16486 | Augmentation | New service connection charges for Aug. Rayan PWSS TW-1 |  |  | BILL/01424/2023-2024 | BP-2023-24-151 | 05/09/2023 | 05/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.11 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF RAYAN (PART-II) PWSS | SM/16486 | Augmentation | Augmentation of RAYAN (PART-II) Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 500 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Burdwan -I Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000183/2024-2025 | 2377/BWD | 25/06/2024 | 22/03/2025 | MATRI ENTERPRISE | 697.52 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF RAYAN (PART-II) PWSS | SM/16486 | Augmentation | Route Survey & Preparation of DPR for RAYAN -PART-II W/S Scheme under Burdwan-I Block under Burdwan Sub-Division under Burdwan Division PHE Dte. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000848/2024-2025 | 2585/BSD | 26/11/2024 | 10/01/2025 | APEX ENGINEERING | 2.95 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF RAYAN (PART-II) PWSS | SM/16486 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2024-2025 | 4101/BWD | 25/11/2024 | 25/11/2024 | Resource Division | 9.24 | 0 | 0 | 0
Total | [13 empty] | 739.03 | 0 | 0