## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF MANGALKOT PIPED WATER SUPPLY SCHEME | SM/16487 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augmentation of Mongolkot Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000120/2023-2024 | 2631/CMD | 13/06/2023 | 13/07/2023 | S.K. ELECTRICALS | 22.05 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF MANGALKOT PIPED WATER SUPPLY SCHEME | SM/16487 | Augmentation | Extension and replacement of pipe line from the existing Distribution System within scheme jurisdiction at Mongalkote village under Mongalkote PWSS under Mongalkote Block within Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-01] | Assistant Engineer |  | ORD/000153/2022-2023 | 437/KTS | 27/06/2022 | 27/07/2022 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 4.84 | 4.81 | 99.36 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF MANGALKOT PIPED WATER SUPPLY SCHEME | SM/16487 | Augmentation | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for Augmentation of Mongalkote & Natunhat and its adjoining mouzas Piped Water Supply Scheme, Block - Mongalkote, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000517/2022-2023 | 4658/BWD | 18/10/2022 | 17/11/2022 | ANIRUDDHA FARUQUE | 13.24 | 8.79 | 66.41 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF MANGALKOT PIPED WATER SUPPLY SCHEME | SM/16487 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme MONGALKOTE PWSS (Sl No-06) | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000074/2023-2024 | 399/KTS | 13/04/2023 | 13/05/2023 | SIRCON ENGINEERING SERVICES | 2.93 | 2.93 | 100 | 100
5 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF MANGALKOT PIPED WATER SUPPLY SCHEME | SM/16487 | Augmentation | Yard lighting arrangement & allied works at Mangalkote water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000410/2024-2025 | 2790/CMD | 01/10/2024 | 30/11/2024 | JAGANNATH ENTERPRISE | 13.47 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF MANGALKOT PIPED WATER SUPPLY SCHEME | SM/16487 | Augmentation | Augmentation of MANGALKOTE Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under MONGALKOTE Block, District:- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000696/2023-2024 | 4365/BWD | 04/10/2023 | 01/04/2026 | M/S NATIONAL CONSTRUCTION | 689.68 | 0 | 0 | 25
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF MANGALKOT PIPED WATER SUPPLY SCHEME | SM/16487 | Augmentation | Different types of works involve in connection with implementation of Aug. Mongalkote, Palishgram, Purba Nowapara, Sitahati, Singhi, Mejhiary & Karui Piped Water Supply Scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001191/2024-2025 | 873/BWD | 06/03/2025 | 02/09/2025 | M/S S. CHOUDHURY | 588.22 | 0 | 0 | 0
Total | [13 empty] | 1334.43 | 16.53 | 1.24