## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR TEANDUL | SM/16489 | Retrofitting | Construction of Path Way, Drain, Repairing of Pump House at 2nd TW Site and Providing leftout FHTC, Road Restoration with allied work for TENDUL Piped Water Supply Scheme, Block- Raina-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000965/2024-2025 | 4375/BWD | 13/12/2024 | 13/03/2025 | DEY NIRMAN | 12.69 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR TEANDUL | SM/16489 | Retrofitting | Construction of Boundary wall at Head Works Site of TEANDUL Water Supply Scheme under RAINA I Block of Burdwan Division, PHE Dte. (Length -151.00 Mtr, Col - 48 Nos). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000012/2023-2024 | 1727/BWD | 13/04/2023 | 12/06/2023 | HI-LIGHT ELECTRONICS | 21.94 | 0 | 0 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR TEANDUL | SM/16489 | Retrofitting | Laying of Parallel Pipeline from Distribution line near Head Work site to Sonadanga to improve water demand at Madubon, Sultanbad & Dhomas village by direct water supply of TENDUL Piped Water Supply Scheme, Raina-I Block under Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001110/2023-2024 | 1117/BWD | 14/03/2024 | 16/07/2024 | ANWESHA CONSTRUCTION | 11.7 | 0 | 0 | 100
Total | [13 empty] | 46.33 | 0 | 0