## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Manteswar | Burdwan Division | KHANPUR PIPED WATER SUPPLY SCHEME | SM/16540 | New | Material Requisition To Resource Division |  |  | RTOR000381/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 11.22 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Manteswar | Burdwan Division | KHANPUR PIPED WATER SUPPLY SCHEME | SM/16540 | New | Material Requisition To Resource Division |  |  | RTOR000531/2023-2024 | 4293/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 2.89 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Manteswar | Burdwan Division | KHANPUR PIPED WATER SUPPLY SCHEME | SM/16540 | New | Material Requisition To Resource Division |  |  | RTOR000558/2023-2024 | 4934/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 67.03 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Manteswar | Central Mechanical | KHANPUR PIPED WATER SUPPLY SCHEME | SM/16540 | New | NEW SERVICE CONNECTION FOR KHANPUR PWSS. |  |  | BILL/02687/2023-2024 | BP-2023-24-562 | 23/02/2024 | 23/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.01 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Manteswar | Central Mechanical | KHANPUR PIPED WATER SUPPLY SCHEME | SM/16540 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at KHANPUR Water Supply Scheme [ Block-MONTESWAR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000799/2023-2024 | 4086/CMD | 29/08/2023 | 28/09/2023 | S DUTTA | 43.47 | 0 | 0 | 65
6 | PURBA BARDHAMAN | Manteswar | Burdwan Division | KHANPUR PIPED WATER SUPPLY SCHEME | SM/16540 | New | KHANPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Monteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER DURGAPUR SUB-DIVISION PHE DTE | ORD/000803/2023-2024 | 4808/BWD | 08/11/2023 | 31/10/2025 | NATIONAL CONSTRUCTION | 707.7 | 0 | 0 | 60
7 | PURBA BARDHAMAN | Manteswar | Central Mechanical | KHANPUR PIPED WATER SUPPLY SCHEME | SM/16540 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 31/10/2025 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
8 | PURBA BARDHAMAN | Manteswar | Central Mechanical | KHANPUR PIPED WATER SUPPLY SCHEME | SM/16540 | New | CONTINUATION OREDER- Hiring of inspection vehicle no. [ WB41H5741] (Diesel/CNG/LPG Driven) for supervision of the site for the office of the Assistant Engineer ,CMD PHE Dte. [W.E.F- 01.08.2025 to 30.09.2025] | ASSISTANT ENGINEER | Junior Engineer | ORD/000131/2025-2026 | 1035/CMSD | 30/07/2025 | 29/09/2025 | PRODYUT GHOSH | 0.8 | 0 | 0 | 0
Total | [13 empty] | 916.18 | 0 | 0