## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina - I | Burdwan Division | NETRAKHANDA PIPED WATER SUPPLY SCHEME | SM/16616 | New | Material Requisition To Resource Division |  |  | RTOR000355/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 7.53 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Raina - I | Burdwan Division | NETRAKHANDA PIPED WATER SUPPLY SCHEME | SM/16616 | New | NETRAKHANDA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Raina-I Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000660/2023-2024 | 4121/BWD | 14/09/2023 | 13/09/2024 | SUJAY KUMAR RAY | 345.67 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Raina - I | Burdwan Division | NETRAKHANDA PIPED WATER SUPPLY SCHEME | SM/16616 | New | Material Requisition To Resource Division |  |  | RTOR000524/2023-2024 | 4290/BWD | 29/09/2023 |  | Resource Division | 2.08 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina - I | Central Mechanical | NETRAKHANDA PIPED WATER SUPPLY SCHEME | SM/16616 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Netrakhanda Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000722/2023-2024 | 4033/CMD | 29/08/2023 | 28/09/2023 | GLACIER ENGINEERING CO | 28.97 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina - I | Burdwan Division | NETRAKHANDA PIPED WATER SUPPLY SCHEME | SM/16616 | New | Material Requisition To Resource Division |  |  | RTOR000682/2023-2024 | 5055/BWD | 23/11/2023 |  | Resource Division | 20.46 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina - I | Central Mechanical | NETRAKHANDA PIPED WATER SUPPLY SCHEME | SM/16616 | New | New Service connection for Netrakhanda W/S Scheme PH No.-II |  |  | BILL/01801/2023-2024 | BP-2023-24-320 | 30/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.85 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina - I | Central Mechanical | NETRAKHANDA PIPED WATER SUPPLY SCHEME | SM/16616 | New | New Service connection for Netrakhanda W/S Scheme PH No.-II |  |  | BILL/01801/2023-2024 | BP-2023-24-320 | 30/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.85 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Raina - I | Central Mechanical | NETRAKHANDA PIPED WATER SUPPLY SCHEME | SM/16616 | New | New Service connection for Netrakahanda W/S Scheme PH No.-I |  |  | BILL/01802/2023-2024 | BP-2023-24-319 | 30/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.7 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Raina - I | Central Mechanical | NETRAKHANDA PIPED WATER SUPPLY SCHEME | SM/16616 | New | New Service connection for Netrakahanda W/S Scheme PH No.-I |  |  | BILL/01802/2023-2024 | BP-2023-24-319 | 30/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.7 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Raina - I | Central Mechanical | NETRAKHANDA PIPED WATER SUPPLY SCHEME | SM/16616 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 25/11/2024 | DEY ENTERPRISE | 74.58 | 0 | 0 | 0
Total | [13 empty] | 500.4 | 0 | 0