## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | NERAGOHALIA PIPED WATER SUPPLY SCHEME | SM/16617 | New | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation, construction of switch room, boundary walls with gates, land development, surface drains and internal pathways at different TW site for NERAGOHALIA Piped Water Supply Scheme under BURDWAN-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000478/2023-2024 | 3493/BWD | 09/08/2023 | 01/10/2026 | M/S ASHA CONSTRUCTION | 577.52 | 207.48 | 35.93 | 55
2 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | NERAGOHALIA PIPED WATER SUPPLY SCHEME | SM/16617 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Neragohalia Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000660/2023-2024 | 4003/CMD | 29/08/2023 | 28/09/2023 | DUTTA ENTERPRISE | 28.98 | 0 | 0 | 60
3 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | NERAGOHALIA PIPED WATER SUPPLY SCHEME | SM/16617 | New | Material Requisition To Resource Division |  |  | RTOR000103/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 18.38 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | NERAGOHALIA PIPED WATER SUPPLY SCHEME | SM/16617 | New | Material Requisition To Resource Division |  |  | RTOR000354/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 20.45 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | NERAGOHALIA PIPED WATER SUPPLY SCHEME | SM/16617 | New | Material Requisition To Resource Division |  |  | RTOR000727/2023-2024 | 5273/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 21.07 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | NERAGOHALIA PIPED WATER SUPPLY SCHEME | SM/16617 | New | Quotation for new service connection at NARAGOHALIA W/S Scheme PH-I. |  |  | BILL/01814/2023-2024 | BP-2023-24-321 | 30/12/2023 | 30/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.28 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | NERAGOHALIA PIPED WATER SUPPLY SCHEME | SM/16617 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 31/10/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | NERAGOHALIA PIPED WATER SUPPLY SCHEME | SM/16617 | New | New service connection charges for Neragohalia PWSS TW-2 |  |  | BILL/02205/2023-2024 | BP-2023-24-391 | 17/01/2024 | 17/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.09 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | NERAGOHALIA PIPED WATER SUPPLY SCHEME | SM/16617 | New | Restoration of Conc. road, Providing leftout FHTC with extension of Pipeline, construction of Pathway, drain, repairing of Pump House at Head Work site with allied works for MAGRA, SANUI, SATGACHIA Zone-I & NARAGOHALIA PIPED WATER SUPPLY SCHEME, Block-Memari-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001192/2024-2025 | 611/BWD | 11/02/2025 | 10/08/2025 | M/S ASHA CONSTRUCTION | 354.13 | 0 | 0 | 25
Total | [13 empty] | 1087.84 | 207.48 | 19.07