## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina-I | Burdwan Division | SIPTA PIPED WATER SUPPLY SCHEME | SM/16618 | New | Material Requisition To Resource Division |  |  | RTOR000155/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 8.72 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Raina-I | Burdwan Division | SIPTA PIPED WATER SUPPLY SCHEME | SM/16618 | New | Material Requisition To Resource Division |  |  | RTOR000694/2023-2024 | 5058/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Raina-I | Central Mechanical | SIPTA PIPED WATER SUPPLY SCHEME | SM/16618 | New | New service connection charges for Sipta PWSS TW-1 |  |  | BILL/00795/2023-2024 | BP-2023-24-88 | 26/07/2023 | 26/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.76 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina-I | Central Mechanical | SIPTA PIPED WATER SUPPLY SCHEME | SM/16618 | New | New service connection charges for Sipta PWSS TW-2 |  |  | BILL/00796/2023-2024 | BP-2023-24-89 | 26/07/2023 | 26/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.07 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina-I | Burdwan Division | SIPTA PIPED WATER SUPPLY SCHEME | SM/16618 | New | Providing 20 Nos.FHTC at SIPTA village for declearation of SWAJALGRAM under SIPTA Piped Water Supply Scheme, Block- Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000514/2024-2025 | 1861/BSD | 22/08/2024 | 21/09/2024 | ROY CONSTRUCTION | 0.96 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina-I | Burdwan Division | SIPTA PIPED WATER SUPPLY SCHEME | SM/16618 | New | SIPTA Single Village Scheme with sinking of Tube-well & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Raina-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000794/2022-2023 | 1444/BWD | 24/03/2023 | 22/06/2023 | S.B. ASSOCIATES | 49.61 | 0 | 0 | 100
7 | PURBA BARDHAMAN | Raina-I | Burdwan Division | SIPTA PIPED WATER SUPPLY SCHEME | SM/16618 | New | SIPTA Single Village Scheme with sinking of LDS, Rising Main and FHTC under Raina-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000100/2023-2024 | 2258/BWD | 18/05/2023 | 16/08/2023 | ROY CONSTRUCTION | 115.09 | 0 | 0 | 100
8 | PURBA BARDHAMAN | Raina-I | Central Mechanical | SIPTA PIPED WATER SUPPLY SCHEME | SM/16618 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sipta Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000147/2023-2024 | 2880/CMD | 07/07/2023 | 06/08/2023 | S.G. ENTERPRISE | 28.95 | 0 | 0 | 95
9 | PURBA BARDHAMAN | Raina-I | Burdwan Division | SIPTA PIPED WATER SUPPLY SCHEME | SM/16618 | New | Construction of approach road near 2nd. Tube well site of SIPTA Water Supply Scheme [New Scheme], Raina-I, under Burdwan Sub Division PHE Dte. under Burdwan Division PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001046/2024-2025 | 211/BWD | 09/01/2025 | 08/02/2025 | SAIKAT RAY | 7.2 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Raina-I | Central Mechanical | SIPTA PIPED WATER SUPPLY SCHEME | SM/16618 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 25/11/2024 | DEY ENTERPRISE | 74.58 | 0 | 0 | 10
11 | PURBA BARDHAMAN | Raina-I | Burdwan Division | SIPTA PIPED WATER SUPPLY SCHEME | SM/16618 | New | Restore of village Road dismalted by laying pipe line at for providing FHTC at Kukre village under SIPTA PIPED WATER SUPPLY SCHEME [new scheme],Block-Raina-I,within Burdwan Sub Division under Burdwan Division PHE Dte. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001174/2024-2025 | 261/BSD | 05/02/2025 | 20/02/2025 | ROY CONSTRUCTION | 0.96 | 0 | 0 | 100
Total | [13 empty] | 312.37 | 0 | 0