## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina-I | Central Mechanical | BAJITPUR PIPED WATER SUPPLY SCHEME | SM/16619 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bajitpur Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000717/2023-2024 | 4028/CMD | 29/08/2023 | 28/09/2023 | SAIKAT ENTERPRISE | 28.98 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Raina-I | Burdwan Division | BAJITPUR PIPED WATER SUPPLY SCHEME | SM/16619 | New | Material Requisition To Resource Division |  |  | RTOR000220/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 11.46 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Raina-I | Burdwan Division | BAJITPUR PIPED WATER SUPPLY SCHEME | SM/16619 | New | Material Requisition To Resource Division |  |  | RTOR000479/2023-2024 | 4003/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 9.08 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina-I | Burdwan Division | BAJITPUR PIPED WATER SUPPLY SCHEME | SM/16619 | New | Material Requisition To Resource Division |  |  | RTOR000647/2023-2024 | 5096/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina-I | Burdwan Division | BAJITPUR PIPED WATER SUPPLY SCHEME | SM/16619 | New | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-09-2024 to 30-11-2024 | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000682/2024-2025 | 1957/BSD | 30/08/2024 | 29/11/2024 | SK. ASFIA | 1.2 | 0.34 | 28.63 | 60
6 | PURBA BARDHAMAN | Raina-I | Central Mechanical | BAJITPUR PIPED WATER SUPPLY SCHEME | SM/16619 | New | New electric connection for Bajitpur PWSS, PH-1. |  |  | BILL/01887/2023-2024 | BP-2023-24-358 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.31 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina-I | Burdwan Division | BAJITPUR PIPED WATER SUPPLY SCHEME | SM/16619 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BAJITPUR, SHUKUR & HARISHNAPUR Piped Water Supply Scheme under RAINA-I Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000388/2023-2024 | 3197/BWD | 24/07/2023 | 16/01/2026 | MRITYUNJOY MUKHERJEE & CO. | 1242.03 | 54.78 | 4.41 | 55
8 | PURBA BARDHAMAN | Raina-I | Burdwan Division | BAJITPUR PIPED WATER SUPPLY SCHEME | SM/16619 | New | Continuation Work Order for Supply of one No.Diesel Driven Ambassador Car No. WB:41H-4009 on hire basis for the office of the Assistant Engineer,Burdwan Sub-Division,PHE Dte (Period from 01-06-2025 to 31.08.2025) |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000180/2025-2026 | 1260/BSD | 30/05/2025 | 30/08/2025 | SK. ASFIA | 1.2 | 0 | 0 | 60
Total | [13 empty] | 1319.73 | 55.13 | 4.18