## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) | SM/16774 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of SAGRAI(Part-B)[KHANDAGHOSH] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000572/2023-2024 | 3898/CMD | 18/08/2023 | 17/09/2023 | M/S, S.S. ENTERPRISE. | 24.41 | 11.98 | 49.08 | 40
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) | SM/16774 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Aug. of SAGRAI W/S Scheme (2ND TW SITE) under Khandaghosh Block within Burdwan Sub-Division, PHE Dte. [For 01 No. Tube well]. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000191/2023-2024 | 2688/BWD | 08/06/2023 | 08/07/2023 | NATIONAL CONSTRUCTION | 13.23 | 10.23 | 77.33 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) | SM/16774 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for SAGRAI its Adjoining Mouza W/S Scheme, Block -Khandaghosh within Burdwan Sub-Division, PHE Dte. (Mouza- Jubila) |  |  | ORD/000769/2022-2023 | 504/BSD | 21/03/2023 | 05/05/2023 | JYOTI ENTERPRISE | 3.5 | 2.76 | 78.79 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) | SM/16774 | Augmentation | Designing, Making and Erection of Sign Board for SAJAL GRAM in Sagrai Village, Khandaghosh Block within Sagrai PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | AE(HQs) | J.E. 1 BURDWAN | ORD/000737/2023-2024 | 830/AE/HQ | 30/10/2023 | 29/11/2023 | ISHAN CONSTRUCTION | 0.76 | 0.72 | 95.4 | 100
5 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) | SM/16774 | Augmentation | New service connection charges for Sagrai W/S Scheme TW-3 |  |  | BILL/00685/2023-2024 | BP-2023-24-27 | 22/06/2023 | 22/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.31 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) | SM/16774 | Augmentation | Repairing damaged concrete road by Cement concrete (mix 1:1.5:3) and drainage system, Sluice valve chamber for FHTC work for KHANDAGHOSH, TARAPOSH, SAGRAI, SANKARI, KHUDKURI, ONARI PWSS and its adjoining mouzas within KHANDAGHOSH BLOCK under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000689/2024-2025 | 3684/BWD | 23/10/2024 | 01/04/2026 | SUPRIYA RAY | 115.68 | 0 | 0 | 20
7 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) | SM/16774 | Augmentation | Illumination arrangement & different electro-mechanical works at SAGRAI water supply scheme under KHANDAGHOSH Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000416/2024-2025 | 2800/CMD | 01/10/2024 | 30/11/2024 | CHOUDHURY ENTERPRISE | 14.29 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) | SM/16774 | Augmentation | Restore of Pipeline damaded by construction of drain by Zilla Parishad near Jobila Muslimpara under SAGRAI Piped Water Supply Scheme, Block- Khandaghosh within Burdwan Sub Division under Burdwan Division PHE Dte | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001027/2023-2024 | 278/BSD | 09/02/2024 | 10/03/2024 | SHUBHRA KANTI GHOSH | 0.96 | 0.4 | 42.25 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) | SM/16774 | Augmentation | Restore of Pipeline damaded by construction of drain by Zilla Parishad near Jobila F.P.School & Peer Tala & Chatimpur under SAGRAI Piped Water Supply Scheme, Block- Khandaghosh within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001177/2023-2024 | 534/BSD | 14/03/2024 | 13/04/2024 | SHUBHRA KANTI GHOSH | 0.94 | 0 | 0 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) | SM/16774 | Augmentation | Repairing damaged concrete road by cement concrete (mix 1:1.5:3) for FHTC work for SAGRAI Piped W/S. Scheme and its adj. mouzas within Khandaghosh Block under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001056/2023-2024 | 895/BWD | 01/03/2024 | 31/03/2024 | SK KHAIRUL ISLAM | 8.78 | 8.71 | 99.23 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) | SM/16774 | Augmentation | Restore of Pipeline damaged by construction of drain by Zilla Parishad near Jobila Sarkarpara under SAGRAI Piped Water Supply Scheme, Block- Khandaghosh within Burdwan Sub Division under Burdwan Division PHE Dte | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001172/2023-2024 | 531/BSD | 14/03/2024 | 13/04/2024 | SHUBHRA KANTI GHOSH | 0.96 | 0.58 | 60.3 | 100
12 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) | SM/16774 | Augmentation | Laying of Rising main in between 3rd Tube Wells to 125 mm dia distribution pipe line at Chatimpur village for SAGRAI Pipe Water Supply scheme in Khandaghosh Block under Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001091/2023-2024 | 516/BSD | 13/03/2024 | 12/04/2024 | SHANKHA GHOSH | 0.97 | 0.91 | 94.09 | 100
13 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) | SM/16774 | Augmentation | Shifting of pipeline of 160mm & 90mm HDPE pipeline for Irrigation canel crossing and special maintenance for FHTC work for Sagrai & Khandaghosh Piped Water Supply Scheme within Khandaghosh block under Burdwan Division, PHE Dte. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000127/2024-2025 | 1008/BSD | 06/06/2024 | 06/07/2024 | SHUBHRA KANTI GHOSH | 0.86 | 0.86 | 100 | 100
14 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) | SM/16774 | Augmentation | Beautification of PWSS with Arboriculture, Recharge Pit including shaft and anciliary works at SAGRAI (Khandaghosh Block) P.W.S.S under Burdwan Division, PHE Dte. |  | Contractual Junior Engineer | ORD/000551/2024-2025 | 282/RWS | 03/09/2024 | 01/01/2025 | ALOKA CONSTRUCTION | 0.97 | 0 | 0 | 100
15 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) | SM/16774 | Augmentation | Replacement of Tube-well & Rising main at HEAD TW SITE, 2ND TW site, 3rd TW site for Khandaghosh PWSS, HEAD TW SITE for Sagrai PWSS, HEAD TW SITE for SANKARI Piped Water Supply Scheme under Khandaghosh Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000438/2024-2025 | 3077/BWD | 09/08/2024 | 16/06/2025 | ANIRUDDHA FARUQUE | 80.21 | 53.83 | 67.11 | 100
16 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) | SM/16774 | Augmentation | Quotation for new service connection for Sagrai PWSS TW-4. |  |  | BILL/00256/2024-2025 | BP-2024-25-135 | 05/06/2024 | 05/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.68 | 0 | 0 | 0
Total | [13 empty] | 272.5 | 90.98 | 33.39