## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF TALIT-SIMDAL PWSS (PART-B) | SM/18112 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17 (Size 3.60 mtr x 3.00 mtr room) for TALIT its Adjoining Mouza W/S Scheme, Block -Bardhaman-I within Burdwan Sub-Division, PHE Dte. (Mouza- TALIT) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000838/2022-2023 | 500/BSD | 21/03/2023 | 05/05/2023 | MAHAKE CONTRACTOR & GENERAL ORDER SUPPLIERS | 3.16 | 2.59 | 81.99 | 100
2 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF TALIT-SIMDAL PWSS (PART-B) | SM/18112 | Augmentation | New service connection charges for Aug. Talit-Simdal PWSS TW-3 |  |  | BILL/00758/2023-2024 | BP-2023-24-58 | 17/07/2023 | 17/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.36 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF TALIT-SIMDAL PWSS (PART-B) | SM/18112 | Augmentation | Illumination arrangement & different electro-mechanical works at TALIT SIMDAL water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000480/2024-2025 | 2957/CMD | 20/11/2024 | 19/01/2025 | SUDIKSHA CONSTRUCTION | 17.91 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF TALIT-SIMDAL PWSS (PART-B) | SM/18112 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of TALIT SIMDAL( Part-B)[BURDWAN-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000570/2023-2024 | 3900/CMD | 18/08/2023 | 17/09/2023 | CINZANO | 22.41 | 10.54 | 47.03 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF TALIT-SIMDAL PWSS (PART-B) | SM/18112 | Augmentation | Balance Work for extension of pipe lines to provide FHTC With Sinking of Tub well , Construction of pump house with Boundary wall & other related work for TALIT-SIMDAL (SM/18112), NABABHAT (SM-15166) and DEWANDIGHI-MIRJAPUR (SM/09494) PWSS under Burdwan Sub-Div., Block -Bwn-1, under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001248/2024-2025 | 793/BWD | 03/03/2025 | 01/07/2025 | M/S S.S. ENTERPRISE | 227.66 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF TALIT-SIMDAL PWSS (PART-B) | SM/18112 | Augmentation | 150MM DI bypass pipeline at KHETIA mouza for smooth water supply for FHTC under KHETIA & Talit Simdal pwss within Bardhaman- I block under Burdwan Division PHE DTE. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001080/2024-2025 | 111/BSD | 16/01/2025 | 15/02/2025 | ROY CONSTRUCTION | 4.77 | 0 | 0 | 100
Total | [13 empty] | 277.27 | 13.13 | 4.74