## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari-I | Burdwan Division | AMADPUR PIPED WATER SUPPLY SCHEME | SM/18146 | New | AMADPUR Piped Water Supply Scheme with sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of 200 cum capacity RCC OHRs with 20.0 mtr. Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site under MEMARI-I Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000569/2023-2024 | 4123/BWD | 14/09/2023 | 01/04/2026 | SUPRIYA RAY | 313.65 | 98.51 | 31.41 | 40
2 | PURBA BARDHAMAN | Memari-I | Central Mechanical | AMADPUR PIPED WATER SUPPLY SCHEME | SM/18146 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for new Tube well no.- 1 & 2 of AMADPUR[MEMARI-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/001089/2023-2024 | 4511/CMD | 06/10/2023 | 05/11/2023 | AMUSAR IMPEX PVT. LTD. | 25.2 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Memari-I | Central Mechanical | AMADPUR PIPED WATER SUPPLY SCHEME | SM/18146 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000100/2024-2025 | 2392/CMD | 02/08/2024 | 31/10/2024 | MITRA ENTERPRISE | 47.62 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari-I | Central Mechanical | AMADPUR PIPED WATER SUPPLY SCHEME | SM/18146 | New | New service connection for Amadpur W/S Scheme. |  |  | BILL/02187/2023-2024 | BP-2023-24-383 | 16/01/2024 | 16/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.47 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Memari-I | Central Mechanical | AMADPUR PIPED WATER SUPPLY SCHEME | SM/18146 | New | New service connection for Amadpur W/S Scheme. |  |  | BILL/02188/2023-2024 | BP-2023-24-382 | 16/01/2024 | 16/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.69 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Memari-I | Burdwan Division | AMADPUR PIPED WATER SUPPLY SCHEME | SM/18146 | New | Material Requisition To Resource Division |  |  | RTOR000043/2024-2025 | 323/BWD | 15/01/2025 | 15/01/2025 | Resource Division | 9.23 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Memari-I | Central Mechanical | AMADPUR PIPED WATER SUPPLY SCHEME | SM/18146 | New | Additional quotation for new service connection at Amadpur PWSS |  |  | BILL/01235/2024-2025 | BP-2024-25-420 | 09/01/2025 | 09/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.2 | 0 | 0 | 0
Total | [13 empty] | 411.06 | 98.51 | 23.96