## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SASANGA PIPED WATER SUPPLY SCHEME | SM/18245 | New | Material Requisition To Resource Division |  |  | RTOR000296/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 6.45 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SASANGA PIPED WATER SUPPLY SCHEME | SM/18245 | New | Material Requisition To Resource Division |  |  | RTOR000405/2023-2024 | 3827/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 17.67 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SASANGA PIPED WATER SUPPLY SCHEME | SM/18245 | New | Material Requisition To Resource Division |  |  | RTOR000574/2023-2024 | 4923/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 41.11 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | SASANGA PIPED WATER SUPPLY SCHEME | SM/18245 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at SASANGA Water Supply Scheme [ Block-KHONDOGHOSH ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000921/2023-2024 | 4185/CMD | 29/08/2023 | 28/09/2023 | P.K. ENGINEERING | 45.37 | 24.01 | 52.92 | 90
5 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | SASANGA PIPED WATER SUPPLY SCHEME | SM/18245 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000064/2024-2025 | 2390/CMD | 02/08/2024 | 31/10/2024 | MS DAS ELECTRIC CO | 46.54 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SASANGA PIPED WATER SUPPLY SCHEME | SM/18245 | New | Material Requisition To Resource Division |  |  | RTOR000005/2024-2025 | 4116/BWD | 25/11/2024 | 25/11/2024 | Resource Division | 22.79 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | SASANGA PIPED WATER SUPPLY SCHEME | SM/18245 | New | Quotation for new service connection for Sasanga PWSS PH 2. |  |  | BILL/00229/2024-2025 | BP-2024-25-120 | 29/05/2024 | 29/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.09 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | SASANGA PIPED WATER SUPPLY SCHEME | SM/18245 | New | New service connection charges for Sasanga PWSS TW-2 |  |  | BILL/02210/2023-2024 | BP-2023-24-401 | 17/01/2024 | 17/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.5 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | SASANGA PIPED WATER SUPPLY SCHEME | SM/18245 | New | New service connection charges for Sasanga PWSS TW-1 |  |  | BILL/02209/2023-2024 | BP-2023-24-400 | 17/01/2024 | 17/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.46 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SASANGA PIPED WATER SUPPLY SCHEME | SM/18245 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ONARI & SASANGA Piped Water Supply Scheme under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000452/2023-2024 | 3430/BWD | 07/08/2023 | 01/10/2025 | M/S JAN MAHAMMAD | 1398.82 | 486.11 | 34.75 | 50
11 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SASANGA PIPED WATER SUPPLY SCHEME | SM/18245 | New | Field level data validation of FHTC executed by Agencies on the basis of pictorial data with the objective of controlling multiple entry,improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database of SASANGA Pipe Water Supply Scheme in Khandaghosh Block within Burdwan Sub-Division under Burdwan Division,PHE Dte |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000894/2024-2025 | 2673/BSD | 04/12/2024 | 29/12/2025 | TECHVISION | 1.48 | 0 | 0 | 100
Total | [13 empty] | 1592.28 | 510.12 | 32.04