## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SASANGA PIPED WATER SUPPLY SCHEME | SM/18245 | New | Material Requisition To Resource Division |  |  | RTOR000296/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 6.45 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SASANGA PIPED WATER SUPPLY SCHEME | SM/18245 | New | Material Requisition To Resource Division |  |  | RTOR000405/2023-2024 | 3827/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 17.67 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SASANGA PIPED WATER SUPPLY SCHEME | SM/18245 | New | Material Requisition To Resource Division |  |  | RTOR000574/2023-2024 | 4923/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 41.11 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | SASANGA PIPED WATER SUPPLY SCHEME | SM/18245 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at SASANGA Water Supply Scheme [ Block-KHONDOGHOSH ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000921/2023-2024 | 4185/CMD | 29/08/2023 | 28/09/2023 | P.K. ENGINEERING | 45.37 | 24.01 | 52.92 | 90
5 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | SASANGA PIPED WATER SUPPLY SCHEME | SM/18245 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000064/2024-2025 | 2390/CMD | 02/08/2024 | 31/10/2024 | MS DAS ELECTRIC CO | 46.54 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SASANGA PIPED WATER SUPPLY SCHEME | SM/18245 | New | Material Requisition To Resource Division |  |  | RTOR000005/2024-2025 | 4116/BWD | 25/11/2024 | 25/11/2024 | Resource Division | 22.79 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | SASANGA PIPED WATER SUPPLY SCHEME | SM/18245 | New | Quotation for new service connection for Sasanga PWSS PH 2. |  |  | BILL/00229/2024-2025 | BP-2024-25-120 | 29/05/2024 | 29/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.09 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | SASANGA PIPED WATER SUPPLY SCHEME | SM/18245 | New | New service connection charges for Sasanga PWSS TW-2 |  |  | BILL/02210/2023-2024 | BP-2023-24-401 | 17/01/2024 | 17/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.5 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | SASANGA PIPED WATER SUPPLY SCHEME | SM/18245 | New | New service connection charges for Sasanga PWSS TW-1 |  |  | BILL/02209/2023-2024 | BP-2023-24-400 | 17/01/2024 | 17/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.46 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SASANGA PIPED WATER SUPPLY SCHEME | SM/18245 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ONARI & SASANGA Piped Water Supply Scheme under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000452/2023-2024 | 3430/BWD | 07/08/2023 | 01/10/2025 | M/S JAN MAHAMMAD | 1398.82 | 486.11 | 34.75 | 50
Total | [13 empty] | 1590.8 | 510.12 | 32.07