## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | ONARI PIPED WATER SUPPLY SCHEME | SM/18246 | New | Material Requisition To Resource Division |  |  | RTOR000359/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 14.41 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | ONARI PIPED WATER SUPPLY SCHEME | SM/18246 | New | Material Requisition To Resource Division |  |  | RTOR000685/2023-2024 | 5075/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | ONARI PIPED WATER SUPPLY SCHEME | SM/18246 | New | Material Requisition To Resource Division |  |  | RTOR000403/2023-2024 | 3829/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 24.57 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | ONARI PIPED WATER SUPPLY SCHEME | SM/18246 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000064/2024-2025 | 2390/CMD | 02/08/2024 | 31/10/2024 | MS DAS ELECTRIC CO | 46.54 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | ONARI PIPED WATER SUPPLY SCHEME | SM/18246 | New | New Service connection for Onari PWSS TW-2. |  |  | BILL/02897/2023-2024 | BP-2023-24-620 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.68 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | ONARI PIPED WATER SUPPLY SCHEME | SM/18246 | New | New service connection for Onari PWSS TW-1. |  |  | BILL/02892/2023-2024 | BP-2023-24-619 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.68 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | ONARI PIPED WATER SUPPLY SCHEME | SM/18246 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ONARI & SASANGA Piped Water Supply Scheme under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000452/2023-2024 | 3430/BWD | 07/08/2023 | 01/10/2025 | M/S JAN MAHAMMAD | 1398.82 | 323.66 | 23.14 | 50
8 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | ONARI PIPED WATER SUPPLY SCHEME | SM/18246 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Onari Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000680/2023-2024 | 4012/CMD | 29/08/2023 | 28/09/2023 | M/S. S.R. ENTERPRISE | 28.09 | 0 | 0 | 95
9 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | ONARI PIPED WATER SUPPLY SCHEME | SM/18246 | New | Supply of flow control devices and CIDF Pipes for ONARI PWSS (SM/18246) under Burdwan Division, PHE Dte._2ND CALL | AE(HQs) | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001024/2024-2025 | 81/AE/HQ | 07/01/2025 | 14/05/2025 | MAKALI ENGINEERING CORPORATION | 9.95 | 0 | 0 | 100
Total | [13 empty] | 1558.21 | 323.66 | 20.77