## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-I,Khandaghosh | Burdwan Division | NALA PIPED WATER SUPPLY SCHEME | SM/18256 | New | Material Requisition To Resource Division |  |  | RTOR000396/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 17.83 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Burdwan-I,Khandaghosh | Burdwan Division | NALA PIPED WATER SUPPLY SCHEME | SM/18256 | New | Material Requisition To Resource Division |  |  | RTOR000412/2023-2024 | 3868/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 3.83 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan-I,Khandaghosh | Burdwan Division | NALA PIPED WATER SUPPLY SCHEME | SM/18256 | New | Material Requisition To Resource Division |  |  | RTOR000679/2023-2024 | 5054/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Burdwan-I,Khandaghosh | Central Mechanical | NALA PIPED WATER SUPPLY SCHEME | SM/18256 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Nala Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000659/2023-2024 | 4002/CMD | 29/08/2023 | 07/02/2025 | P.K. ENGINEERING | 28.89 | 11.4 | 39.47 | 95
5 | PURBA BARDHAMAN | Burdwan-I,Khandaghosh | Central Mechanical | NALA PIPED WATER SUPPLY SCHEME | SM/18256 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 31/10/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan-I,Khandaghosh | Central Mechanical | NALA PIPED WATER SUPPLY SCHEME | SM/18256 | New | New service connection at NALA PWSS Ph-2 |  |  | BILL/02328/2023-2024 | BP-2023-24-445 | 29/01/2024 | 29/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.37 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Burdwan-I,Khandaghosh | Central Mechanical | NALA PIPED WATER SUPPLY SCHEME | SM/18256 | New | New service connection at NALA PWSS Ph-1 |  |  | BILL/02327/2023-2024 | BP-2023-24-444 | 29/01/2024 | 29/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.2 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Burdwan-I,Khandaghosh | Burdwan Division | NALA PIPED WATER SUPPLY SCHEME | SM/18256 | New | Balance work i.e. Extension or parallel Pipeline, Leftout FHTC, Road Restoration work, Sinking of Additional Tube Well with Pump House & Boundary wall, Solar System with structure, inter Connection of Additional Tube Well, & allied work for NALA Piped Water Supply Scheme under Burdwan Sub Division, PHE Dte. within Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001266/2024-2025 | 847/BWD | 05/03/2025 | 03/07/2025 | DIAMOND ENGINEERS CO-OP SOCIETY LTD. | 184.95 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Burdwan-I,Khandaghosh | Burdwan Division | NALA PIPED WATER SUPPLY SCHEME | SM/18256 | New | Material Requisition To Resource Division |  |  | RTOR000026/2024-2025 | 305/BWD | 15/01/2025 | 15/01/2025 | Resource Division | 1.97 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Burdwan-I,Khandaghosh | Burdwan Division | NALA PIPED WATER SUPPLY SCHEME | SM/18256 | New | NALA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Burdwan-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000425/2023-2024 | 3327/BWD | 02/08/2023 | 01/01/2027 | MD HASIN | 752.05 | 277.01 | 36.83 | 75
Total | [13 empty] | 1074.51 | 288.41 | 26.84