## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | JIUDHARA PWSS | SM/18314 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at JIUDHARA Water Supply Scheme [ Block- KALNA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000900/2023-2024 | 4164/CMD | 29/08/2023 | 28/09/2023 | DUTTA ENTERPRISE | 44.4 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | JIUDHARA PWSS | SM/18314 | New | Material Requisition To Resource Division |  |  | RTOR000295/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 18.12 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | JIUDHARA PWSS | SM/18314 | New | Material Requisition To Resource Division |  |  | RTOR000629/2023-2024 | 4877/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 26.94 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | JIUDHARA PWSS | SM/18314 | New | Material Requisition To Resource Division |  |  | RTOR000525/2023-2024 | 4291/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 50.47 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | JIUDHARA PWSS | SM/18314 | New | New service connection for Jewdhara PWSS PH-1 |  |  | BILL/02314/2023-2024 | BP-2023-24-458 | 30/01/2024 | 30/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.55 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | JIUDHARA PWSS | SM/18314 | New | JIUDHARA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Kalna II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000719/2023-2024 | 4534/BWD | 13/10/2023 | 01/12/2025 | SOMNATH ROY CHOWDHURY | 625.16 | 108.02 | 17.28 | 45
7 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | JIUDHARA PWSS | SM/18314 | New | Different Types of work involved in connection with Augmentation of 6 Nos. [(SM/07827), (SM/07866), (SM/16196), (SM/18314), (SM/16021), (SM/16019)] Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001144/2024-2025 | 618/BWD | 11/02/2025 | 10/08/2025 | M/S DATTA ENTERPRISE | 578.09 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Kalna-II | Central Mechanical | JIUDHARA PWSS | SM/18314 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000116/2024-2025 | 2393/CMD | 02/08/2024 | 09/05/2025 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 0 | 20
9 | PURBA BARDHAMAN | Kalna-II | Burdwan Division | JIUDHARA PWSS | SM/18314 | New | Work order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR JIUDHARA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000961/2024-2025 | 1231/KSD | 27/09/2024 | 12/10/2024 | DEL DELTA CONSTRUCTION | 0.66 | 0 | 0 | 100
Total | [13 empty] | 1429.21 | 108.02 | 7.56