## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | BALIDANGA PIPE WATER SUPPLY SCHEME | SM/18315 | New | Material Requisition To Resource Division |  |  | RTOR000409/2023-2024 | 3871/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 88.34 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | BALIDANGA PIPE WATER SUPPLY SCHEME | SM/18315 | New | Material Requisition To Resource Division |  |  | RTOR000225/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 13.45 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | BALIDANGA PIPE WATER SUPPLY SCHEME | SM/18315 | New | Material Requisition To Resource Division |  |  | RTOR000649/2023-2024 | 5097/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 19.96 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | BALIDANGA PIPE WATER SUPPLY SCHEME | SM/18315 | New | Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/001080/2023-2024 | 22/KTS | 05/01/2024 | 15/03/2024 | AJIT SAMANTA | 0.9 | 0.3 | 33.4 | 100
5 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | BALIDANGA PIPE WATER SUPPLY SCHEME | SM/18315 | New | NEW SERVICE CONNECTION FOR BALIDANGA PWSS. |  |  | BILL/02474/2023-2024 | BP-2023-24-530 | 13/02/2024 | 13/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.7 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | BALIDANGA PIPE WATER SUPPLY SCHEME | SM/18315 | New | NEW SERVICE CONNECTION FOR BALIDANGA PWSS. |  |  | BILL/02475/2023-2024 | BP-2023-24-531 | 13/02/2024 | 13/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12.76 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | BALIDANGA PIPE WATER SUPPLY SCHEME | SM/18315 | New | BALIDANGA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mongolkote Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000457/2023-2024 | 3439/BWD | 08/08/2023 | 01/04/2026 | M/S S.S. ENTERPRISE | 567.39 | 242.94 | 42.82 | 27
8 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | BALIDANGA PIPE WATER SUPPLY SCHEME | SM/18315 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BALIDANGA Water Supply Scheme [ Block- MANGOLKOTE ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000883/2023-2024 | 4146/CMD | 29/08/2023 | 14/03/2025 | CHOUDHURY ENTERPRISE | 29.7 | 11.54 | 38.85 | 46
9 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | BALIDANGA PIPE WATER SUPPLY SCHEME | SM/18315 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 19/05/2025 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
10 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | BALIDANGA PIPE WATER SUPPLY SCHEME | SM/18315 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-3 at Balidanga Water Supply Scheme [ BLOCK- Mangalkote ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/001395/2024-2025 | 884/CMD | 26/03/2025 | 25/05/2025 | M/S, S.S. ENTERPRISE. | 12.3 | 0 | 0 | 0
Total | [13 empty] | 807.15 | 254.77 | 31.56