## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Balgana Piped Water Supply Scheme | SM/18326 | New | Material Requisition To Resource Division |  |  | RTOR000224/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 3.74 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Balgana Piped Water Supply Scheme | SM/18326 | New | Material Requisition To Resource Division |  |  | RTOR000402/2023-2024 | 3830/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 19.8 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Balgana Piped Water Supply Scheme | SM/18326 | New | Material Requisition To Resource Division |  |  | RTOR000648/2023-2024 | 5111/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Balgana Piped Water Supply Scheme | SM/18326 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Replacement T.W of Bolgona Water Supply Scheme(H.W site) [ BLOCK- Bhatar] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000529/2024-2025 | 3069/CMD | 03/12/2024 | 01/02/2025 | CHOUDHURY ENTERPRISE | 18.41 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Balgana Piped Water Supply Scheme | SM/18326 | New | New service connection charges for Balgana PWSS TW-2 |  |  | BILL/02206/2023-2024 | BP-2023-24-403 | 17/01/2024 | 17/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.86 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Balgana Piped Water Supply Scheme | SM/18326 | New | Quotation for new service connection at Augmentation of Balgona PWSS PH-4 |  |  | BILL/00391/2024-2025 | BP-2024-25-208 | 18/07/2024 | 18/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.22 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Balgana Piped Water Supply Scheme | SM/18326 | New | New service connection charges for Balgona PWSS TW-1 |  |  | BILL/01829/2023-2024 | BP-2023-24-339 | 06/01/2024 | 06/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.44 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | Balgana Piped Water Supply Scheme | SM/18326 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BALGANA & GANGPUR Piped Water Supply Scheme under Burdwan ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000538/2023-2024 | 3699/BWD | 24/08/2023 | 01/10/2025 | SUPRITI ENTERPRISE | 1345.79 | 0 | 0 | 20
9 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Balgana Piped Water Supply Scheme | SM/18326 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Balgana Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000669/2023-2024 | 4007/CMD | 29/08/2023 | 01/04/2025 | GLACIER ENGINEERING CO | 28.96 | 0 | 0 | 95
10 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | Balgana Piped Water Supply Scheme | SM/18326 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 31/10/2024 | DILIP MAHATO | 53.14 | 0 | 0 | 12
Total | [13 empty] | 1505.82 | 0 | 0