## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | BAGHTONA PIPED WATER SUPPLY SCHEME | SM/18334 | New | Material Requisition To Resource Division |  |  | RTOR000215/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 1.33 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | BAGHTONA PIPED WATER SUPPLY SCHEME | SM/18334 | New | Material Requisition To Resource Division |  |  | RTOR000432/2023-2024 | 3854/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 39.78 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | BAGHTONA PIPED WATER SUPPLY SCHEME | SM/18334 | New | Additional Quotation for new service connection charges for Baghtona PWSS TW-1 |  |  | BILL/01421/2023-2024 | BP-2023-24-145 | 31/08/2023 | 31/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.9 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | BAGHTONA PIPED WATER SUPPLY SCHEME | SM/18334 | New | New service connection charges for Baghtona PWSS TW-1 |  |  | BILL/01422/2023-2024 | BP-2023-24-149 | 01/09/2023 | 01/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.36 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | BAGHTONA PIPED WATER SUPPLY SCHEME | SM/18334 | New | Additional quotation for Baghtona PWSS TW-1 |  |  | BILL/01543/2023-2024 | BP-2023-24-210 | 01/11/2023 | 01/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | BAGHTONA PIPED WATER SUPPLY SCHEME | SM/18334 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BAGHTONA, & KASIGRAM Piped Water Supply Scheme under Katwa ¿ I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000390/2023-2024 | 3199/BWD | 24/07/2023 | 01/01/2025 | MANASH GHOSH | 1161.82 | 0 | 0 | 95
7 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | BAGHTONA PIPED WATER SUPPLY SCHEME | SM/18334 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 31/10/2024 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | BAGHTONA PIPED WATER SUPPLY SCHEME | SM/18334 | New | Material Requisition To Resource Division |  |  | RTOR000019/2024-2025 | 4105/BWD | 25/11/2024 | 25/11/2024 | Resource Division | 11.5 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | BAGHTONA PIPED WATER SUPPLY SCHEME | SM/18334 | New | NEW SERVICE CONNECTION FOR BAGHTONA PWSS TW-2 |  |  | BILL/00127/2024-2025 | BP-2024-25-61 | 26/04/2024 | 26/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.01 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | BAGHTONA PIPED WATER SUPPLY SCHEME | SM/18334 | New | Continuation work order for Supply of 1 (one) No. Diesel driven Ambassador Car (Luxury Taxi) / Motor Cab on hire basis for the Office of the Assistant Engineer, under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.07.2025 to 31.12.2025]. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000319/2025-2026 | 1595/KTS | 30/06/2025 | 31/12/2025 | KRISHNA MONDAL | 2.4 | 0 | 0 | 33
11 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | BAGHTONA PIPED WATER SUPPLY SCHEME | SM/18334 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BAGHTONA Water Supply Scheme [ Block- KATWA-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Driller In-Charge | Junior Engineer | ORD/000597/2023-2024 | 3954/CMD | 24/08/2023 | 30/04/2025 | SOUNAK ENTERPRISE | 28.48 | 0 | 0 | 44
Total | [13 empty] | 1310.74 | 0 | 0