## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | BAINCHI PIPED WATER SUPPLY SCHEME | SM/18335 | New | BAINCHI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Katwa-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE,Junior Engineer, R.W.S., Katwa-I Dev. Block | ORD/000486/2023-2024 | 3503/BWD | 10/08/2023 | 01/10/2025 | MAA ENGINEERS CO. OPERATIVE & CONSTRUCTION SOCIETY LTD. | 521.7 | 110.59 | 21.2 | 75
2 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | BAINCHI PIPED WATER SUPPLY SCHEME | SM/18335 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BAINCHI Water Supply Scheme [ Block- KATWA-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Driller In-Charge | Junior Engineer | ORD/000885/2023-2024 | 4148/CMD | 29/08/2023 | 07/09/2025 | M/S, S.S. ENTERPRISE. | 30.35 | 0 | 0 | 88
3 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | BAINCHI PIPED WATER SUPPLY SCHEME | SM/18335 | New | Material Requisition To Resource Division |  |  | RTOR000219/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 13.1 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | BAINCHI PIPED WATER SUPPLY SCHEME | SM/18335 | New | Material Requisition To Resource Division |  |  | RTOR000506/2023-2024 | 4030/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 46.22 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | BAINCHI PIPED WATER SUPPLY SCHEME | SM/18335 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 31/10/2024 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | BAINCHI PIPED WATER SUPPLY SCHEME | SM/18335 | New | New service connection charges for Bainchi PWSS TW-1 |  |  | BILL/00826/2024-2025 | BP-2024-25-325 | 03/10/2024 | 03/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.89 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | BAINCHI PIPED WATER SUPPLY SCHEME | SM/18335 | New | New service connection charges for Bainchi PWSS TW-2 |  |  | BILL/00827/2024-2025 | BP-2024-25-324 | 03/10/2024 | 03/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.75 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | BAINCHI PIPED WATER SUPPLY SCHEME | SM/18335 | New | CONTINUATION ORDER-Hiring of inspection vehicle bearing no. WB41H5698 (Diesel/CNG/LPG Driven) for supervision of JJM works under the jurisdiction of the Assistant Engineer, CMSD,P.H.E. Dte. [W.E.F-01/09/2025 TO 31/10/2025 ] | ASSISTANT ENGINEER | Junior Engineer | ORD/000280/2025-2026 | 1166/CMSD | 25/08/2025 | 25/10/2025 | SUBRATA BHADRA | 0.81 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | BAINCHI PIPED WATER SUPPLY SCHEME | SM/18335 | New | Emmergent LDS work for continuation of pipe line between Chandrapur and Kamal by laying of 200 mm dia. Di pipe and other ancillary work under BAINCHI PWSS (SM/18335) under Katwa-I Block, District:- Purba-Bardhaman | Assistant Engineer | Junior Engineer, R.W.S., Katwa-I Dev. Block | ORD/001318/2024-2025 | 984/BWD | 13/03/2025 | 14/05/2025 | BABLU KUMAR MONDAL | 9.24 | 0 | 0 | 97
10 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | BAINCHI PIPED WATER SUPPLY SCHEME | SM/18335 | New | Material Requisition To Resource Division |  |  | RTOR000080/2024-2025 | 406/BWD | 17/01/2025 | 17/01/2025 | Resource Division | 2 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | BAINCHI PIPED WATER SUPPLY SCHEME | SM/18335 | New | Operation of Distribution System , Rising main, Sluice Valves, including operation of sluice valves of BAICHI PWSS under Katwa-I Block within Katwa Sub-Division under Burdwan Division, PHE Dte. [Period 01.02.2026 to 31.05.2026 i e 04(Four) Months] |  |  | ORD/001283/2025-2026 | 82/KTS | 30/01/2026 | 30/05/2026 | MAA ENGINEERS CO. OPERATIVE & CONSTRUCTION SOCIETY LTD. | 0.93 | 0 | 0 | 0
Total | [13 empty] | 691.14 | 110.59 | 16