## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina-I | Burdwan Division | BELSHAR PIPED WATER SUPPLY SCHEME | SM/18338 | New | Material Requisition To Resource Division |  |  | RTOR000423/2023-2024 | 3860/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 3.41 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Raina-I | Burdwan Division | BELSHAR PIPED WATER SUPPLY SCHEME | SM/18338 | New | Material Requisition To Resource Division |  |  | RTOR000247/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 1.8 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Raina-I | Burdwan Division | BELSHAR PIPED WATER SUPPLY SCHEME | SM/18338 | New | Material Requisition To Resource Division |  |  | RTOR000654/2023-2024 | 5100/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina-I | Central Mechanical | BELSHAR PIPED WATER SUPPLY SCHEME | SM/18338 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Belshar Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000719/2023-2024 | 4030/CMD | 29/08/2023 | 15/12/2024 | SINHA ELECTRICALS | 28.97 | 25.18 | 86.91 | 96
5 | PURBA BARDHAMAN | Raina-I | Burdwan Division | BELSHAR PIPED WATER SUPPLY SCHEME | SM/18338 | New | Material Requisition To Resource Division |  |  | RTOR000006/2024-2025 | 4115/BWD | 25/11/2024 | 25/11/2024 | Resource Division | 21.15 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina-I | Central Mechanical | BELSHAR PIPED WATER SUPPLY SCHEME | SM/18338 | New | New electric connection for Belswar PWSS, PH-1. |  |  | BILL/01872/2023-2024 | BP-2023-24-360 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.01 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina-I | Central Mechanical | BELSHAR PIPED WATER SUPPLY SCHEME | SM/18338 | New | NEW SERVICE CONNECTION FOR BELSHAR PWSS TW 2. |  |  | BILL/03182/2023-2024 | BP-2023-24-666 | 22/03/2024 | 22/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.39 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Raina-I | Central Mechanical | BELSHAR PIPED WATER SUPPLY SCHEME | SM/18338 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 25/11/2024 | DEY ENTERPRISE | 74.58 | 0 | 0 | 10
9 | PURBA BARDHAMAN | Raina-I | Burdwan Division | BELSHAR PIPED WATER SUPPLY SCHEME | SM/18338 | New | Balance work [i.e. Extension or parallel Pipeline, Leftout FHTC, Road Restoration work, Sinking of Additional Tube Well with Pump House & Boundary wall, inter Connection of Additional Tube Well, Construction of M.S.Structural bridge, canal Crossing, MS casing with allied work of Bhagabatipur, Machkhara, Udgara, Bantir, Chakpurohit Rasuikhanda, Sankarpur, Gopalpur & Belshar PWSS Block-RAINA- I under Burdwan Sub Division, PHE Dte. within Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001103/2024-2025 | 469/BWD | 24/01/2025 | 01/04/2027 | SK ALIM | 1353.91 | 0 | 0 | 55
10 | PURBA BARDHAMAN | Raina-I | Burdwan Division | BELSHAR PIPED WATER SUPPLY SCHEME | SM/18338 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BELSHAR & SANKARPUR Piped Water Supply Scheme under Raina ¿ I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000411/2023-2024 | 3256/BWD | 27/07/2023 | 01/08/2026 | SK ALIM | 1345.74 | 541.33 | 40.23 | 85
Total | [13 empty] | 2866.41 | 566.51 | 19.76