## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram-I | Central Drilling | EHIAPUR PIPED WATER SUPPLY SCHEME | SM/18342 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Ehiapur W/S Scheme (T/W-I & II) ,Ketugram-I Block under PurbaBardhman District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000163/2023-2024 | 1348/CDD | 13/09/2023 | 13/10/2023 | CHANDA ENTERPRISE | 16.67 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | EHIAPUR PIPED WATER SUPPLY SCHEME | SM/18342 | New | Material Requisition To Resource Division |  |  | RTOR000250/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 4.15 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | EHIAPUR PIPED WATER SUPPLY SCHEME | SM/18342 | New | Material Requisition To Resource Division |  |  | RTOR000398/2023-2024 | 3874/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 64.94 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | EHIAPUR PIPED WATER SUPPLY SCHEME | SM/18342 | New | Material Requisition To Resource Division |  |  | RTOR000576/2023-2024 | 4924/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 40.35 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | EHIAPUR PIPED WATER SUPPLY SCHEME | SM/18342 | New | New service connection charges for Ehiapur PWSS TW-1 |  |  | BILL/01470/2023-2024 | BP-2023-24-168 | 27/09/2023 | 27/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.42 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | EHIAPUR PIPED WATER SUPPLY SCHEME | SM/18342 | New | EHIAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000456/2023-2024 | 3438/BWD | 08/08/2023 | 07/08/2024 | M/S S.S. ENTERPRISE | 732.05 | 606.31 | 82.82 | 75
7 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | EHIAPUR PIPED WATER SUPPLY SCHEME | SM/18342 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 31/10/2024 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | EHIAPUR PIPED WATER SUPPLY SCHEME | SM/18342 | New | Material Requisition To Resource Division |  |  | RTOR000013/2024-2025 | 4111/BWD | 25/11/2024 | 25/11/2024 | Resource Division | 9.24 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | EHIAPUR PIPED WATER SUPPLY SCHEME | SM/18342 | New | New service connection charges for Ehiapur PWSS TW-3 |  |  | BILL/01726/2023-2024 | BP-2023-24-258 | 07/12/2023 | 07/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.52 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | EHIAPUR PIPED WATER SUPPLY SCHEME | SM/18342 | New | New service connection charges for Ehiapur PWSS TW-2 |  |  | BILL/01727/2023-2024 | BP-2023-24-259 | 07/12/2023 | 07/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.82 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | EHIAPUR PIPED WATER SUPPLY SCHEME | SM/18342 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at EHIAPUR Water Supply Scheme [ Block- KETUGRAM-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000843/2023-2024 | 4115/CMD | 29/08/2023 | 05/05/2025 | ASHIM UDYOG | 44.39 | 35.13 | 79.14 | 61
12 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | EHIAPUR PIPED WATER SUPPLY SCHEME | SM/18342 | New | Balance Work For OHR, Extension Of Pipeline To Provide FHTC With Sinking Of Tube Well, Construction Of Pump House, Boundary Wall, Land Development, Plinth Protection For Pump House, Approach Road & Other Related Work Under Bakalsa, Chakdaha, Ehaipur, Khatundi And Ketugram (Zone-I) Part-A & B PWSS Under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000288/2024-2025 | 2741/BWD | 12/07/2024 | 01/01/2026 | M/S M.M. ENTERPRISE | 205.15 | 7.34 | 3.58 | 65
Total | [13 empty] | 1213.98 | 648.78 | 53.44