## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Manteswar | Central Mechanical | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. | SM/18365 | New | Supply and delivery of Stationary items for the official works related with Mirghar and differents water supply scheme under JJM Programme for Central Mechanical Division and its subordinate offices of P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001033/2023-2024 | 702/CMSD | 17/08/2023 | 27/08/2023 | BURDWAN DISTRICT CENTRAL SERVICE CUM MARKETING INDUSTRIAL CO-OPARETIVE UNION LTD | 0.74 | 0.74 | 100 | 100
2 | PURBA BARDHAMAN | Manteswar | Burdwan Division | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. | SM/18365 | New | Material Requisition To Resource Division |  |  | RTOR000357/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 19.8 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Manteswar | Burdwan Division | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. | SM/18365 | New | Material Requisition To Resource Division |  |  | RTOR000461/2023-2024 | 3985/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 262.83 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Manteswar | Central Mechanical | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. | SM/18365 | New | New service connection charges for Mirghar PWSS TW-2 |  |  | BILL/01368/2023-2024 | BP-2023-24-134 | 24/08/2023 | 24/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.42 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Manteswar | Central Mechanical | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. | SM/18365 | New | New service connection charges for Mirghar PWSS TW-3 |  |  | BILL/01369/2023-2024 | BP-2023-24-135 | 24/08/2023 | 24/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.29 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Manteswar | Burdwan Division | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. | SM/18365 | New | MIRGAHAR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 700 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls and land development, drain and internal pathway at different TW site under Monteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000374/2023-2024 | 3104/BWD | 19/07/2023 | 18/07/2024 | M/S S. CHOUDHURY | 929.46 | 482.99 | 51.96 | 60
7 | PURBA BARDHAMAN | Manteswar | Central Mechanical | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. | SM/18365 | New | continuation order Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of Assistant Engineer, under C.M.D. P.H.E. Dte. w.e.f.- 01/01/2024 to 29/02/2024. [Under JJM Works] | ASSISTANT ENGINEER | Junior Engineer | ORD/001636/2023-2024 | 1240/CMSD | 31/12/2023 | 29/02/2024 | SUBRATA BHADRA | 0.79 | 0.79 | 99.86 | 100
8 | PURBA BARDHAMAN | Manteswar | Central Mechanical | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. | SM/18365 | New | Supply and installation of Electro-Magnetic flow meter at AURIA, KARUI & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000602/2024-2025 | 3106/CMD | 11/12/2024 | 09/02/2025 | S.K. ELECTRICALS | 13.6 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Manteswar | Burdwan Division | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. | SM/18365 | New | Different types of works in connection with implementation of MIRGAHAR Piped Water Supply Scheme (SM/18365) & BAGPUR PWSS (SM/13323) under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000186/2024-2025 | 2400/BWD | 26/06/2024 | 24/10/2024 | M/S S. CHOUDHURY | 301.24 | 85.64 | 28.43 | 60
10 | PURBA BARDHAMAN | Manteswar | Central Mechanical | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. | SM/18365 | New | NEW SERVICE CONNECTION FOR MIRGHAR PWSS |  |  | BILL/02591/2023-2024 | BP-2023-24-552 | 20/02/2024 | 20/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.8 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Manteswar | Central Mechanical | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. | SM/18365 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1,2, 3 & 4 at MIRGHAR Water Supply Scheme [ Block- MONTESWAER] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000467/2023-2024 | 3724/CMD | 08/08/2023 | 07/09/2023 | P.K. ENGINEERING | 59.87 | 36.16 | 60.39 | 75
12 | PURBA BARDHAMAN | Manteswar | Central Mechanical | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. | SM/18365 | New | Supply and installation of Electro-Magnetic flow meter at Bazar Mahammadpur, Dhatrigram, Arjunpukur & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000590/2024-2025 | 3105/CMD | 11/12/2024 | 09/02/2025 | SHREE BISHNU CONSTRUCTION | 19.77 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Manteswar | Central Mechanical | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. | SM/18365 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 31/10/2025 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
Total | [13 empty] | 1703.68 | 606.32 | 35.59