## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | KASIGRAM PIPE WATER SUPPLY SCHEME | SM/18367 | New | Material Requisition To Resource Division |  |  | RTOR000318/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 11.67 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | KASIGRAM PIPE WATER SUPPLY SCHEME | SM/18367 | New | Material Requisition To Resource Division |  |  | RTOR000431/2023-2024 | 3855/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 68.67 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | KASIGRAM PIPE WATER SUPPLY SCHEME | SM/18367 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BAGHTONA, & KASIGRAM Piped Water Supply Scheme under Katwa ¿ I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000390/2023-2024 | 3199/BWD | 24/07/2023 | 01/01/2025 | MANASH GHOSH | 1161.82 | 610.45 | 52.54 | 95
4 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | KASIGRAM PIPE WATER SUPPLY SCHEME | SM/18367 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 31/10/2024 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | KASIGRAM PIPE WATER SUPPLY SCHEME | SM/18367 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at KASIGRAM Water Supply Scheme [ Block-KATWA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000881/2023-2024 | 4144/CMD | 29/08/2023 | 02/01/2025 | M/S. SWAPAN BANERJEE | 45.09 | 37.53 | 83.25 | 90
6 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | KASIGRAM PIPE WATER SUPPLY SCHEME | SM/18367 | New | Material Requisition To Resource Division |  |  | RTOR000020/2024-2025 | 4104/BWD | 25/11/2024 | 25/11/2024 | Resource Division | 6.95 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | KASIGRAM PIPE WATER SUPPLY SCHEME | SM/18367 | New | New service connection for Kasigram PWSS PH-1. |  |  | BILL/02909/2023-2024 | BP-2023-24-616 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.69 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | KASIGRAM PIPE WATER SUPPLY SCHEME | SM/18367 | New | New service connection for Kasigram PWSS PH-3. |  |  | BILL/02907/2023-2024 | BP-2023-24-618 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.73 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | KASIGRAM PIPE WATER SUPPLY SCHEME | SM/18367 | New | New service connection for Kashigram PWSS PH-2. |  |  | BILL/02908/2023-2024 | BP-2023-24-617 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.06 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | KASIGRAM PIPE WATER SUPPLY SCHEME | SM/18367 | New | Continuation work order for Supply of 1 (one) No. Diesel driven Ambassador Car (Luxury Taxi) / Motor Cab on hire basis for the Office of the Assistant Engineer, under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.07.2025 to 31.12.2025]. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000319/2025-2026 | 1595/KTS | 30/06/2025 | 31/12/2025 | KRISHNA MONDAL | 2.4 | 0 | 0 | 33
Total | [13 empty] | 1360.24 | 647.98 | 47.64